## 1.0 Document Control
Process: Preopening Hotel
Process Owner: SVP Operations |  | Process Leader: Responsible of the involved area
Author | Beatriz Sánchez-Herrera Saeta
Date | December.2018
Last modification date | March 2022
Document version | 5
Scope
* This procedure applies to all NHHG hotels that undertake a long-term opening process. In the case of the take over openings, the times and deadlines will be adjusted to the dates and requirements, defined in the contract, so that all main tasks can be carried out accurately. * This document includes all the main tasks (critical path) and communication flows that have to be performed in the opening of a hotel by each area and department responsible, setting deadlines, methodologies, templates, etc. * Due to the complexity of the process and the diversity of the areas involved, this document must be considered as the global framework to apply in each opening and could be improved (if it's neccesary) with the local tasks or other occasional tasks defined in the Hotel contract (taking care that the critical path tasks are not modified without a prior approval).
NH Approvals
Name | Function | Date | Comments
Fernando Córdova | Chief People Officer | December.2018
Jesús López | SVP Legal Affairs |  | Pending Approval
Antonio Gutiérrez | SVP Taxes | December.2018
Luis Martínez | SVP Treasury & Financing | December.2018
Francisco Morillo | SVP Administration | December.2018
Ramón Luengo | CEO Coperama Holding | December.2018
Otón Gómez | SVP E-Commerce & Marketing Services | December.2018
Ioana Georgescu | VP MKT Strategy Brand & Product | December.2018
Judith Güemes | VP CRM & Loyalty | December.2018
Javier Mármol | VP Experience & Quality | December.2018
Lucas Miguel Martínez | VP Corporate Affairs & Communications | December.2018
Ana Morillo | VP Commercial Strategy & Pricing | December.2018
Maite Aguilar | VP Distribution | December.2018
Marta Marcos | SVP IT & Systems |  | Pending Approval
Pedro Marfany | SVP Operations | December.2018
Alu Rodríguez | SVP Business Transformation | December.2018
Pilar Rodríguez | SVP Projects, Construction, Maintenance & Engineering | December.2018
Modification History
Document Version | Date | Modified by | Comments
4 | May 2021 | Rocío Rilo | Loyalty tasks update (Discovery program)
5 | March 2022 | Pilar Jarillo | Experience & PCM&E tasks update
Business Processes - Operations

## PreOpening Team Template
Process: Preopening Hotel
Process Owner: SVP Operations Process Leader: Responsible of the involved area
HOTEL DATA |  | INTEGRATION TEAM |  | JIRA TICKETS RELATED
Hotel Name: |  | General Manager: |  | Administration:
Category / Brand: |  | Regional Operations Director: |  | TMS4Hotels:
Nº Rooms: |  | Operations Director: |  | TMS4Meetings:
Hotel Code: |  | Managing Director: |  | Users:
City: |  |  |  | Stay Options:
BU: |  |  |  | Online Check In:
Contract Type: |  |  |  | TMS4Loyalty:
Opening Date: |  |  |  | Others:
PREOPENING TEAM
The preopening tasks will begin around 365 days before the opening and the first one will be the creation of the PreOpening Team. The PreOpening Team will be composed of one member of each BU department to coordinate the entire opening process from the beginning to the end. Weekly, biweekly or monthly meetings will be held to know which tasks are completed and which not, and so, follow-up and comply with the established times. Within this team, the member of the Operations department will be the leader and will be responsible of fulfilling the next template, reporting it to all the departments involved.
AREAS / DEPARTEMENTS | FULL NAME | POSITION | E-MAIL CONTACT | PHONE NUMBER CONTACT
OPERATIONS & GLOBAL TRANSFORMATION
IT & Systems
Operations
Business Transformation
Projects, Construction, Maintenance & Engineering
Business Intelligent
MARKETING & COMMUNICATION
E-Commerce & Marketing Services
Strategy Brand & Product
CRM & Loyalty
Experience & Quality
Corporate Affairs & Communications
COMMERCIAL
Business Development
Distribution
Commercial Strategy & Pricing
Forecasting & Optimization
FINANCE
Taxes
Treasury & Financing
Administration & Procure to Pay
Coperama
HUMAN RESOURCES
Internal Communication & Corporate Responsibility
Talent, Learning & Development
Corporate Compensation & HR Analysis
LEGAL
Internal Audit
Legal Affairs
Compliance & Data Protection
ASSETS & DEVELOPMENT
Development
Development & Corporate
Assets Management
Business Processes - Operations

## Com. & Corp.Affairs
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task | Task Description | When (days before opening event) | Responsible | Departments Involved | Tools
1 | Opening Communication | Receive from Legal department the e-mail with the signed contract confirmation | Once the contract is signed | Legal Director | All company areas | E-Mail
2 | Define What Events Will Take Place | Depending on the characteristics and needs of the hotel, it is defined what expenses and what kind of events are carried out or not for the inauguration. All tasks defined later, will be applied only if the Com.&Corp.Affairs department together with the Operations department approve it. | Once the hotel opening information is known | Comms Manager HQ/BU, Institutional Relations & GM | Com. & Corp.Affairs Operations | N/A
3 | Room Reservations | Room reservations for press, key contacts, board of directors, Chefs... (if necessary) | 90 | Comms Manager HQ/BU, Institutional Relations & GM | Com. & Corp.Affairs Operations | N/A
5 | Pre-event Meetings or Letters | Pre-event meetings/letters to gain institutional support and attendance | 90 | Institutional Relations Manager HQ/BU | Com. & Corp.Affairs | N/A
6 | Guest List Preparation | Guest list preparation: Media contacts, institutional contacts, Executive Committee contacts, key staff and board members | 90 | Comms Manager HQ/BU & Institutional Relations | Com. & Corp.Affairs | N/A
7 | Local Activities for International Press | Local activities for international press beyond the event (site inspection to another hotels, tours…) | 60 | Comms Manager HQ/BU | Com. & Corp.Affairs | N/A
8 | "Save the Date" Design and Send Out | Teaser / "save the date" design and send out | 60 | Comms Manager HQ/BU & Institutional Relations | Com. & Corp.Affairs | N/A
9 | Inauguration Plaque Production | Inauguration Plaque Production | 30 | Marcom BU | Com. & Corp.Affairs | N/A
10 | International Chefs Needs | If International chefs travel: hotel to coordinate and order for HQ the ingredients and material needed for the chefs gastro experiences | 30 | Institutional Relations Manager HQ & GM | Com. & Corp.Affairs Operations | N/A
11 | Coordination with Hotel | Booked rooms and meeting spaces, F&B, event outline, protocol, transfer needs, definition of roles with hotel staff…. | 30 | Comms Manager HQ/BU, Institutional Relations & GM | Com. & Corp.Affairs Operations | N/A
12 | Invitation Design and Send Out | Invitation design and send out | 15 | Comms Manager HQ/BU & Institutional Relations | Com. & Corp.Affairs | N/A
13 | Thank You Letter Creation | Thank you letter design. Send after event | 10 | Institutional Relations Manager HQ | Com. & Corp.Affairs | N/A
14 | Material for Tell the World Newsletter | Material for Tell the World Newsletter: editorial, video… Send after event | 10 | Comms Manager HQ/BU & Institutional Relations | Com. & Corp.Affairs | N/A
15 | Attendance Follow Up | Attendance follow up (reminder) | 7 | Comms Manager HQ/BU & Institutional Relations | Com. & Corp.Affairs | N/A
16 | Press Conference | Press conference | 0 | Comms Manager HQ/BU | Com. & Corp.Affairs | N/A
17 | F&B Services for Event | F&B services for event | 0 | Comms Manager HQ/BU & GM | Com. & Corp.Affairs Operations | N/A
18 | Events | Hotel Inauguration - Institutional Event | 0 | Institutional Relations Manager HQ/BU | Com. & Corp.Affairs | N/A
19 | Site Inspection | Site Inspection for press, VIPs, guests… | 0 | Comms Manager & GM | Com. & Corp.Affairs Operations | N/A
20 | Media Interviews | Media interviews | 0 | Comms Manager HQ/BU | Com. & Corp.Affairs | N/A
21 | Social Event | Social Event | 0 | Marcom BU & GM | Com. & Corp.Affairs Operations | N/A
22 | Gift to Attendees | Gift to attendees, linked to concept and product (if applicable) | 0 | Marcom BU | Com. & Corp.Affairs | N/A
23 | Coverage Report | Coverage Report | 0 | Comms Manager HQ/BU | Com. & Corp.Affairs | N/A
The dates established are based on the opening event day, not the hotel opening day
Business Processes - Operations

## Commercial
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task | Task Description | When (days before opening) | Responsible | Departments Involved | Tools
1 | Opening Communication | Receive from Legal department the e-mail with the signed contract confirmation | Once the contract is signed | Legal Director | All company areas | E-Mail
2 | Set Business Plan | Business mix strategy General Manager and Revenue Manager and build action plan | 365 | Regional Revenue Manager | Revenue | N/A
3 | B2B Negotiation Contracts | Ensure B2B Negotiation Contracts status meet target | 350 | Regional Director of Sales & General Manager & Regional Revenue Manager | Sales - Actions | N/A
4 | Strategy & Action Plan | Complete Sales and Marketing Strategic Action Plan | 270 | Regional Director of Sales & Director Business Development | Sales - Actions | N/A
5 | Strategy & Action Plan | Complete Strategic Revenue Plan | 270 | General Manager & Regional Director of Sales & Director Business Development & Director Revenue Manager | Sales - Actions | N/A
6 | Hotel Positioning (I) | Prepare Hotel Positioning presentation | 270 | Regional Director of Sales & Marketing Director | Sales - External Communication | N/A
7 | Segments Actions (I) | - Implement actions for Corporate/Government segment - Implement actions for M&E segment - Implement actions for Leisure Group /Tour Series segment - Implement actions for Wholesale segment | 270 | Director of Sales M&E & Regional Director of Sales & Director of Sales Leisure | Sales - Actions | N/A
8 | Tradeshow Calendar | Review annual Tradeshow calendar and define potential activities to join; always with the approval of the DBD and alignment with HQ | 270 | Regional Director of Sales & Director Business Development | Sales - Actions | N/A
9 | MR&RS Setup | Fill out MR&RS to setup the hotel and open a JIRA with it and share with all the departments involved | 240 | Revenue Manager & Revenue Manager Systems & Front Office Manager | Revenue Operations | MR&RS template NH Service Desk
10 | Distribution Channels Management | Fill out Templates for GDS and DCM to manage hotel in the distribution channels | 210 | DCM / GDS | Commercial - Distribution Operations | N/A
11 | Channels Creation | - Ask to channels creation of new hotel (OTA's, Wholesalers, tour operators, GDS) - Ask channels to load rates | 200 | DCM / GDS | Commercial - Distribution Sales | N/A
12 | Hotel Products | Understand overall hotel product (rooms, F&B, facilities) | 200 | Regional Revenue Manager & General Manager & Regional Director of Sales & Group Sales Office | Sales - Actions | N/A
13 | S&M Pre-opening Budgets | Review and approve Sales and Marketing pre-opening budgets， | 200 | Regional Director of Sales | Sales - Actions | N/A
14 | SWOT Analysis | Create SWOT Analysis | 200 | Regional Director of Sales & General Manager | Sales - Actions | N/A
15 | Guarantee & Cancellation Policy | Define Guarantee & Cancellation Policy | 200 | Revenue Manager | Revenue | N/A
16 | Pricing | Define Breakfast pricing strategy | 200 | Regional Revenue Manager | Revenue | N/A
17 | Pricing | Create all the Public Rates (Pricing 3.0) | 198 | Revenue Manager Systems | Revenue | N/A
18 | Public Contracts Creation | Create all the Public Contracts | 190 | CDM | CDM | N/A
19 | Revenue Manager Position and Training Plan | - Assignment and hiring of Revenue Manager - Plan trainings and introduction of RM if it is a new employee | 180 | Regional Revenue Manager | Revenue | N/A
20 | Competitors - External Site Inspection | Visit the competitor Hotels | 180 | Revenue Manager | Revenue Operations | N/A
21 | Competitors - Benchmarking | Benchmarking: Product, Room Types, Location, F&B Offer… | 180 | Strategic Analyst | Revenue Operations | N/A
22 | Competitors - Compset | Define a primary and secondary compset | 180 | Regional Director of Sales & Director Revenue Manager | Revenue Sales Operations | N/A
23 | Room Category Selling Strategy | Set room category selling strategy per Room Type | 180 | Revenue Manager | Revenue | N/A
24 | Revenue Planning Sections | Complete F&B and C&E Revenue Planning sections | 180 | General Manager & Operations | Sales Operations | N/A
25 | Determine Hotel Spaces Configuration | Determine guest room, meeting space, F&B Outlets configuration | 180 | Operations | Sales - External Communication Operations | N/A
26 | Shuttle Service and Transportation Needs | Determine the need for shuttle service and transportation for market needs | 180 | General Manager & Operations | Sales - External Communication | N/A
27 | Competitors - Benchmarking | Benchmark rate: Track competitor hotel rates for COR and BGR segments | 180 | Regional Director of Sales & Regional Revenue Manager | Sales - Actions | N/A
28 | Segments Actions (II) | - Implement actions for Transient segment - Implement Sales & Marketing Plan - Implement actions for Airline segment | 180 | Marketing & Regional Director of Sales & Director of Sales Airlines | Sales - Actions | N/A
29 | Site Inspection and FAM Trips | Schedule hotel visits and FAM (familiarity) trips for key customers and media | 180 | Regional Director of Sales | Sales - External Communication | N/A
30 | Sales Tracking Sheet | Maintain a Sales Tracking Sheet for all pre-opening sales leads and bookings | 180 | Regional Director of Sales | Sales - Actions | N/A
31 | S&M Action Plan | Sales and Marketing action plan follow up | 180 | Regional Director of Sales | Sales - Actions | N/A
32 | NH Regional Sales Office Presentations | Complete NH Regional Sales Office presentations | 180 | Regional Director of Sales | Sales - Actions | N/A
33 | Feeder Markets per Segment | Identify feeder markets per segment (COR, M&E, Airlines & TO) | 180 | Regional Director of Sales | Sales - Actions | N/A
34 | Business Case | Transient: When opportunities have been identified prepare business cases to request the hotel to get included into the travel program for the company. Bear in mind that the travel programs are yearly and business cases need to be submitted on March latest to be considered to the following year. | 180 | Regional Director of Sales | Sales - Actions | N/A
35 | Negotiation Contract List | List with all existing negotiation in the hotel (PID, name, rates) and copy all the contract existing in SAP as CHAIN or Country (where the new hotel is opened). Only apply if the hotel exist. | 180 | CDM | Commercial - Services | N/A
36 | Competitors - Benchmarking | Benchmark price structure: B2C+B2B | 160 | Revenue Manager | Revenue | N/A
37 | Pricing Strategy | Discuss pricing strategy and development. Prepare rates for key segments and packages. | 160 | Director Revenue Manager & Regional Revenue Manager | Revenue | N/A
38 | Hotel Pricing | Approve hotel pricing by DRM | 160 | Director Revenue Manager | Revenue | N/A
39 | Competitors - Benchmarking | Benchmarking: Rate shopping, market penetration, accounts, web page… | 160 | Revenue Manager | Revenue | N/A
40 | Demand Calendar | Create demand calendar including seasonality studies by RM | 160 | Revenue Manager | Revenue | N/A
41 | Online Agencies Activation | Follow up status of activation of Online Agencies | 160 | DCM / GDS | Commercial - Distribution Sales | N/A
42 | Ice Portal Photos | Photo upload to ICE PORTAL | 160 | GDS | Commercial - Distribution | Ice Portal
43 | Rates | - Define and send FIT/LGR Rates and send to Leisure Sales including close out dates - Define & send COR Rates and send to Corp. Sales including close out dates | 150 | Regional Revenue Manager | Revenue Sales | N/A
44 | DDR | Define the Daily Delegate Rate | 150 | Revenue Manager | Revenue | N/A
45 | Rates | Create Opening Special rates for Transient, Corporate, Meetings, Weddings | 150 | Revenue Manager | Revenue | N/A
46 | Packages creations | Discuss creation of packages (Non-Mandatory) with hotel | 150 | Revenue Manager | Revenue | N/A
47 | Conference Rental Rates | Conference Rental Rates | 150 | Revenue Manager | Revenue | N/A
48 | Pricing | - Banquet Prices - F&B Prices | 150 | Revenue Manager | Revenue Operations - F&B | N/A
49 | Pricing | Define Pricing calendar per day for the coming 18 months | 150 | Revenue Manager | Revenue | N/A
50 | Duetto Contract | Sign contract of the Revenue Management System - Duetto | 150 | Dir. Revenue Systems & Tools | Revenue | Duetto
51 | NH Game Changer Configuration | Activate Hotel in NH Game Changer | 150 | Revenue Manager Systems | Revenue | NH Game Changer
52 | Hotel Positioning (II) | Complete hotel positioning, get approval from DBD | 150 | General Manager | Sales - Internal&Corp. H.O. Operations | N/A
53 | Meeting with the Owner | Set up meeting with Owner to present NH and hotel Sales and Marketing plan | 150 | Regional Director of Sales & General Manager & Regional Revenue Manager | Sales - Internal&Corp. H.O. | N/A
54 | S&M Members | Plan on boarding for new Sales and Marketing team members | 150 | Regional Director of Sales | Sales - Actions | N/A
55 | Local Area Sales | Conduct Local Area Sales Blitz | 150 | Regional Director of Sales | Sales - Actions | N/A
56 | S&M Standard Operating Procedures | Implement Sales & Marketing Standard Operating Procedures (SOP) | 150 | Regional Director of Sales & General Manager | Sales - Actions | N/A
57 | Opportunities from Local Companies | Explore potential opportunities from local companies | 150 | Regional Director of Sales | Sales - Actions | N/A
58 | Channels Content | Channels content | 150 | BU Sales Distribution | Commercial - Distribution Sales | N/A
59 | Lanyon Information Migration | Identify if the hotel had previously Lanyon access, if yes we will request to Lanyon to migrate all the info under the NH brand and afterwards we will update the info (property information) sent in the BUD report. Only apply if the hotel exist. | 150 | LANYON / hotel | Commercial - Services | Lanyon
60 | TMC's that are Fee | Invite all TMC's that are Fee per performance | 150 | LANYON | Commercial - Services | N/A
61 | Rate Loading | Update rate loading templates and minimum RFP information | 150 | LANYON | Commercial - Services | N/A
62 | Data Feed | Open a JIRA - Data feed HIST / SYNC / BK (Activate datafeed from TMS to Duetto) | 141 | Revenue Manager Systems | Commercial - Systems | NH Service Desk (JIRA)
63 | Switch Letter | Send SWITCH letter to each GDS in case of change of CHAIN | 136 | GDS | Commercial - Distribution | N/A
64 | Hotel Configuration to Channels | Export hotel configuration to channels | 135 | GDS | Commercial - Distribution | GDS, DHISCO, Lanyon
65 | Hotel Master Sheet | Hotel Master sheet with the equivalences between TRUST codes and MTS4H | 135 | GDS | Commercial - Distribution | NH Service Desk (JIRA)
66 | Contract | Copy all the contract existing in SAP as CHAIN or Country (where the new hotel is opened). Only apply if the hotel is a new property. | 135 | CDM | Commercial - Services | N/A
67 | Communication | Receive from IT Applications that the system is ready for external clients copy, rate creation, contracts extension and sales strategy creation | 135 | IT Front Office Manager | IT Applications Revenue CDM | N/A
68 | Strategy | Load strategy in Duetto and TMS and indirect channels | 130 | Revenue Manager | Revenue | Duetto, TMS, Synexis
69 | Strategy | Load meeting room strategy in TMS | 130 | Revenue Manager | Revenue | TMS
70 | Strategy | Load groups and meeting rooms strategy in Instant Booking tool | 130 | Revenue Manager | Revenue | Instant Booking Tool
71 | Strategy | Load loyalty rates to the GHA web sales channel | 120 | General Manager & Revenue Manager | Revenue | discoveryloyalty.com
72 | Overbooking Strategy | Set overbooking strategy | 130 | Revenue Manager | Revenue | N/A
73 | B2B Digital Channels | Assure that the hotels are included in B2B Digital Channels (Companies -YS, Agencies-YAS) | 130 | IT Connectivity & Ecommerce Product Dev | B2B Digital Sales | B2B
74 | Mapping | Verify that all contracts and rates that should be available in these channels are mapped in TMS and Tridion | 130 | B2B Digital Sales Director | B2B Digital Sales | B2B, TMS, Tridion
75 | Mapping | Complete and upload the mapping tables | 130 | GDS | Commercial - Distribution | N/A
76 | Duetto Configuration | Configuration TMS Transactions - Duetto | 130 | Revenue Manager Systems | Commercial - Systems | Duetto
77 | OTA's User | Communicate user for all departments in OTA´s, Trust (this user will be informed by DCM / GDS) | 125 | Regional Revenue Manager | Revenue | N/A
78 | M&E Instant Booking Tool | Verify that the hotel rooms and meetings rooms are included in M&E Instant Booking Tool (White label) | 125 | BU M&E Segment Leader & HQ Manager M&E Digital Sales | B2B Digital Sales | M&E Instant Booking Tool
79 | Simulate Reservations | Simulate reservations in each GDS to be sure that the hotel is available and bookable | 125 | GDS | Commercial - Distribution | GDS
80 | Access Trust | Communicate to hotel and RM their TRUST user and password | 125 | GDS | Commercial - Distribution | N/A
81 | Channel Manager System Configuration | Sign contract and setup channel manager system | 120 | Revenue Manager & Regional Revenue Manager | Revenue | N/A
82 | Contracts | Contract rateshopper (B2C and Groups), agency 360, Demand 360 | 120 | Regional Revenue Manager | Revenue | N/A
83 | Competitors - Benchmarking | Benchmarking: Rate shopper, Demand 360, OTA extranet COMPSET | 120 | Revenue Manager | Revenue | N/A
84 | Configuration | Complete Room Type Build | 120 | Operations & Director Revenue Manager | Sales - External Communication | N/A
85 | Sales Activation | Confirm sale activation date, open availability/house status | 120 | General Manager & Operations & Revenue Manager | Sales - External Communication Operations | N/A
86 | Room Type Workbook | Send room type workbook to revenue & sales team for approval | 120 | General Manager & Operations | Sales - External Communication Revenue | N/A
87 | Pre-opening Expenses Budget | Complete Pre-opening Expenses budget | 120 | Director Business Development & Director Revenue Manager | Sales - Actions | N/A
88 | Hotel Gifts | Select the goodies for clients/accounts | 120 | Regional Director of Sales & General Manager | Sales - External Communication Marketing | N/A
89 | CRO&GSO Presentation | Complete NH Central Reservation Office (CRO) presentation & GSO | 120 | Regional Director of Sales | Sales - Actions | N/A
90 | Duetto Set-Up | Fill out "On Boarding Document" to setup hotel in Duetto | 100 | Revenue Manager Systems | Commercial - Systems | Duetto
91 | TMS Set-Up | Fill out Meal Plan document to setup in TMS | 100 | Revenue Manager Systems | Commercial - Systems | Duetto, TMS
92 | Strategy | Build strategy and implement packages & Opaque rates on OTA´s (Expedia, Atrapalo, Top Secret) | 100 | Revenue Manager | Revenue | N/A
93 | Performance Targets | Complete performance targets for hotel Sales team | 100 | Director Business Development | Sales - Sales Actions | N/A
94 | Sales Database | Create a Sales Database for direct mail to potential customers | 100 | Director Business Development & Regional Director of Sales | Sales - Actions | N/A
95 | Revenue Meetings | Set and start Revenue Meetings | 90 | Revenue Manager | Revenue | N/A
96 | Sales Kit | Confirm and approve the text for Sales Kit content sent by Hotel Opening Performance | 60 | Regional Director of Sales | Sales - External Communication Marketing | N/A
97 | Sales Calls | Second round sales call neighbourhood city | 60 | Regional Director of Sales | Sales - Actions | N/A
98 | Meeting with Authorities | Meet with government and local authorities to build relationship | 60 | Regional Director of Sales & General Manager | Sales - Actions | N/A
99 | Sales Calls | Schedule General Manager to join sales calls to key clients | 60 | Regional Director of Sales & General Manager | Sales - Actions | N/A
100 | Reports | Request Business Intelligent HQ the relevant reports to follow up with the business | 60 | Regional Director of Sales | Sales - Actions | N/A
101 | Objectives | Define objectives in regards to MPI, ARI and RGI for current year and coming 2 years | 30 | Regional Revenue Manager | Revenue | N/A
102 | Hotel and Compset Registration | Register hotel and competitive set with Smith Travel Research (STR) Global, send Matrix to HQ RM Tools and systems | 30 | Strategic Analyst | Revenue | Smith Travel Research (STR) Global
103 | Hotel creation in Lanyon | Create the hotel in Lanyon and inform it when created in order they fill in the BUD info. Only apply if the hotel is a new property. | 30 | Lanyon | Commercial - Services | Lanyon
104 | Special Guest Conditions | Determine VIP, regular and long staying guest criteria and policy | 30 | Regional Director of Sales & General Manager | Sales - Actions | N/A
105 | On the Books Report | Send to GM weekly on the books report to hotels showing pre-sell performance (if bookings have started) | 30 | Director Revenue Manager & Regional Director of Sales | Sales - Actions Operations | N/A
106 | Site Inspection | Site Inspection training to the team | 30 | Regional Director of Sales & General Manager | Sales - Actions | N/A
107 | Materials | Receive from Trade Marketing all materials | 30 | Regional Director of Sales & General Manager | Sales - Actions | N/A
108 | Brandcenter Photos | Photo download from Brandcenter | 21 | GDS | Commercial - Distribution | Brandcenter
109 | Upselling Online Training | Ensure that all Front office employees have done de Upselling online training | 20 | Revenue Manager | Revenue | N/A
110 | Upselling | - Define the upselling services and prices according to NHHG strategy: by contact point: Web-CRO-Hotel - Define Upselling objectives by concept and month and send to af.herrera@nh-hotels.com - Request for the creation of the stay options (Through Jira, adding af.herrera@nh-hotels.com as participant) - Manage the configuration of the stay options with IT | 10 | Revenue Manager | Revenue | N/A
111 | Access CGW | Ask for the user name and password to access and create events in - CGW - Customized Group Website, or if centralized in a GSO they should have access | 10 | BU Ecommerce Manager | B2B Digital Sales | NH Service Desk (JIRA)
Business Processes - Operations

## Marketing
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task | Task Description | When (days before opening) | Responsible | Departments Involved | Tools
1 | Opening Communication | Receive from Legal department the e-mail with the signed contract confirmation | Once the contract is signed | Legal Director | All company areas | E-Mail
2 | Iristrace Registration | Register hotel in Iristrace Tool | Once the contract is signed | HQ QA | Marketing - Quality | Iristrace
3 | Mock-up Room Visit | Mock-up room visit | When available | BU QA & GM | Marketing - Quality | N/A
4 | Legal Topics Clearance | Legal topics clearance - Database integrations, local legislation | 365 | Key User BU | CRM & Loyalty Legal | N/A
5 | Hotel Mkt, Commercial & Rev Management 2Y Strategy Plan | Hotel Marketing, Commercial & Rev Management 2Y Strategy Plan | 365 | Marketing Director | Marketing - Hotel Business Strategy | Templates available by brand at Brand Center intranet
6 | Marketing Plan & Budget | Marketing plan and budget preparation and approval | 365 | Marketing Director | Marketing - Marketing Plan&Budget | N/A
7 | Loyalty Call Center Special Languages Adaptation | Loyalty Call Center special languages adaptation (If apply) | 300 | Key User BU | CRM & Loyalty | N/A
8 | Cover pages and templates for quotations | Create cover pages (task only applies for nhow and collection) and templates for quotations | 230 | Marketing Director BU | Marketing - Branding | N/A
9 | Hotel Stationary & Internal Comm Materials | Develop and adapt, when necessary, all Hotel Stationary & Internal Comm Materials, based on Brand Corporate Identity Manual & Brand Operational Standards | 180 | Brand Manager | Marketing - Branding | Brand Center Artworks Templates
10 | Hotel Name & Signage Proposal (I) | Hotel name & signage proposal send to corporate marketing according to methodology (fill in dedicated form, involving indicated departments and Legal Advisors) | 180 | Marketing Director | Marketing - Branding | N/A
11 | Hotel Name & Signage Proposal (II) | Internal communication of hotel name and signage executional requirements, post-approval by Brand Strategy HQ | 180 | Marketing Director | Marketing - Branding | N/A
12 | Outlet Names Proposal | Propose Outlet Names in English and/or local language (Restaurants, Spas…) Check Trademark with Legal Advisor. Naming and Logo to be approved by Brand Strategy HQ | 180 | Marketing Director | Marketing - Branding | N/A
13 | Brand Standards | Check Brand Standards and point out local / regional needs of adjustment | 180 | Marketing Director | Marketing - Branding | N/A
14 | Brand Corporate Identity Manual Translation | Translate and adapt to local language when necessary the Brand Corporate Identity Manual, uploading CIM local language version in BC with HQ approval /revision | 180 | Marketing Director | Marketing - Branding | N/A
15 | Construction & Hotel Signage | Construction site signage - hotel brand billboard Construction site signage - building canvas / billboards (opening soon) Hotel External Signage entrance Hotel External Signage top building Hotel in-house Digital Signage Video / Slide Show | 180 | Marketing Director | Marketing - Advertising | Brand Center
16 | Global & Local Trade Fairs Calendar | Knowledge of Global & Local Trade fairs calendar; detect regional opportunities | 180 | Marketing Director | Marketing - Trade Marketing | N/A
17 | Configuration Templates | Fill out the "BUD Complete", "Master Room & Rate Sheet", "CONTENT - Hotel Director Questionnaire", "CONTENT - Hotel Opening Questionnaire" and "Bank details" templates to create new content for web and OTAS and translations into local languages and send document to DCM Team and Content Team members | 180 | ECommerce Manager BU & Content HQ & GM | E-Commerce Commercial - Distribution Operations | Templates: BUD complete, Master room & rate sheet, CONTENT - Hotel Director Questionnaire and CONTENT - Hotel Opening Questionnaire and "Bank details.
18 | Content NH Website | Once the NH Website is created by content department, coordinate with ecommerce manager BU to load and check pictures | 160 | Content HQ & ECommerce Manager BU | E-Commerce | NH Website
19 | General Information | Receive information about rate structure of hotel (public and group rates) | 130 | Revenue Manager | E-Commerce Commercial - Revenue | Public Rates Set-up
20 | General Information | Receive information about tax treatment (both VAT and city tax if applies) | 130 | E-Commerce Manager BU & Taxes BU | E-Commerce Finances - Taxes | N/A
21 | General Information | Receive information about data for online payments (Amex and Elavon E-commerce Web MIDs) | 130 | Treasury HQ | E-Commerce Finances - Treasury | N/A
22 | Profile Creations | Create/update hotel profile in major portals such as TripAdvisor, Facebook, Holiday check, trivago, Kayak, yelp, Google MyBusiness, foursquare etc. | 130 | Performance Marketing Manager | E-Commerce | TripAdvisor, Holiday check, trivago, Kayak, yelp, Google MyBusiness, foursquare
23 | Paid Traffic Campaigns Configuration | Configure paid traffic campaigns (incl. Google Search, Trivago, TripAdvisor, Feeds) | 130 | Performance Marketing Manager | E-Commerce | Google Search, Trivago, TripAdvisor, Feeds…
24 | Metas search content | Metas search content Loading by BU & HQ | 130 | E-Commerce Manager | E-Commerce | N/A
25 | Hotels Renders Developed | Make available Hotels Renders developed by Projects Department or external partner | 90 | Marketing Director | Marketing - Advertising | Brand Center
26 | Generic Information | Generic Hotel Brochure ( mind endorsement logos: regional or international prizes, networks) Generic Hotel Fact Sheet Pre-opening Generic Hotel Brochure format eBook + downloadable pdf F&B Special Occasions Brochure (Christmas…) Social Events Ppt / Pdf Social Events Quotation template Wellness - Spa & Fitness Brochure Spa / Fitness Fact Sheet /Rate Card | 90 | Marketing Director | Marketing - Advertising | Brand Center
27 | Hotel Information | M&E Hotel Fact Sheet M&E Hotel Brochure / eBook Hotel ppt / pdf Hotel Brochures' Folder Hotel A4 Folder Hotel A4 Trade Offers Template Hotel Quotations & Answers Hotel F&B Offers Special Offers / announcements - emailing footers Template | 90 | Marketing Director | Marketing - Advertising | Brand Center
28 | Give-away List | Hotel give-away List aligned with Brand Standards (HQ Guidelines available) | 90 | Marketing Director | Marketing - Trade Marketing | Guidelines
29 | DDBB registration & Official Communication | Register hotel in DDBB and send Official Communication to rest of Departments | 90 | HQ QA | Marketing - Quality | N/A
30 | DISCOVERY kickoff session | Explain the Loyalty program to the hotels. Overview of main integration milestones. | 60 | CRM & Loyalty | CRM & Loyalty | DISCOVERY Loyalty procedure MS Teams
31 | DISCOVERY Loyalty legal requirement | If the hotel is management contract, the property must complete and sign the Minor Statement of Services (Order Form). | The signature's contract sign | CRM & Loyalty | CRM & Loyalty | Minor Hotels Statement of Services
32 | GHA Hotel Integration templates | Fill in and sign GHA Hotel Form in GHA Discovery in a Box app. | 90 | CRM & Loyalty | CRM & Loyalty | GHA Hotel Form
|  | Fill in and sign GHA Mapping Workbook in GHA Discovery in a Box app - ONLY if hotel does not work with TMS. | 90 | CRM & Loyalty | CRM & Loyalty | GHA Mapping Workbook
|  | Fiin in and sign GHA Property Workbook in GHA Discovery in a Box app. | 90 | CRM & Loyalty | CRM & Loyalty | GHA Property Workbook
33 | Develop Local Experiences and Local Offers | Develop 5 Local Experiences (3 Platinum 2 Black) Develop 4 Local Offers (Live Local) | 60 | GM / Experience BU/ Marketing BU | CRM & Loyalty / Marketing / Experience | Manual and Guide of Local Experiences DISCOVERY Stay Options CMS Template
34 | Families, Welcome | Supervise the correct implementation of families operational promise : kids corner, kids amenities… | 60 | Marketing Director & MKT Experience BU | Marketing - Experience Revenue | Guidelines / Brand Center
35 | FASTPASS Initiatives: OCI & CYR | Request first training (floorplans) Upload floor plans and features for OCI / CYR and deploy OCO roll out. Supervise Priority Desk order - Maintenance Order and place Comm. Materials - Marketing BU | 60 | Marketing Director & GM | Marketing - Experience IT Business Transformation - S&T | Floor Plan Digitalization Guidelines
Brand Center
36 | Hotel Photo Shooting | Hotel photo shooting by professional photographer based on Brand Visual Photographic Guidelines (available at Brand Center) | 45 | Marketing Director | Marketing - Advertising | Brand Visual Photographic Guidelines at Brand Center
37 | Welcome corner | Supervise execution to assure alignment with guidelines, correct postition at the lobby, and correct signage according to brand center | 45 | BU Quality responsible | Marketing - Experience | Guidelines / Brand Center
38 | Breakfast sigange & Fresh corner | Supervise breakfast signage inlcuding the new fresh corner (if applies) is correctly executed and with the correct signage | 45 | BU Quality responsible | Marketing - Experience | Guidelines / Brand Center
39 | Sensory Branding (Music) | Supervise excution: Music for different areas of the hotel homologated provider (The Sensory Lab) | 45 | BU Quality responsible | Marketing - Experience | N/A
40 | Sensory Branding (Fragance) | Supervise excution: Fragrance (if applied) is the homologated one | 45 | BU Quality responsible | Marketing - Experience | N/A
41 | Lobbies Alive | Signage materials and Extras (WiFi, chargers, entertainment…) | 45 | Marketing Director & MKT experience BU | Marketing - Experience PCM&E | Guidelines
42 | Press Reader | Check project for deployment and supervise execution (contract service + marketing materials) | 45 | Marketing Director & MKT experience BU | Marketing - Experience | Guidelines
43 | Analyse the Promotions Inclusion | - Top Destinations campaigns - Smart Choice - Pop-up Days - Summer / Winter | 40 | Marketing Director | Marketing - Promotions | N/A
44 | Media Plan Preparation & Approval | Media plan preparation and approval. Consult Media Packs available at HQ for Hotel Launch (Web Media) | 40 | Marketing Director | Marketing - Media Plan | N/A
45 | Photo Uploading to Brand Center | Photo uploading to Brand Center for approval by Advertising HQ (at least 24 high quality photos) | 30 | Marketing Director | Marketing - Advertising | Brand Center
46 | Campaigns Information | Press Ad campaign Masters (vertical & horizontal) On-line campaign masters (banners / rich media all formats; mind new formats Skinz, Facebook Canvas...) Outdoor campaigns masters (vertical & horizontal) Radio special actions - master brand / hotel messages TV special actions master brand / hotel messages | 30 | Marketing Director | Marketing - Advertising | Brand Center
47 | Loyalty Materials | Loyalty materials (Collaterals, video…) localization based on the Guideline. | 30 | BU Quality responsible | CRM & Loyalty | Guideline
48 | Quality Focus On-line Registration | Register hotel in Quality Focus On-line Tool | 30 | HQ QA | Marketing - Quality | Quality Focus On-Line
49 | TrustYou Registration | Register hotel in TrustYou Tool | 30 | HQ QA | Marketing - Quality | TrutYou
50 | Set Up Quality KPI's Targets | Set Up Quality KPI's Targets and present to hotel team | 30 | BU QA & GM | Marketing - Quality | N/A
51 | OTA's Content Check | Check OTA's and Review Sites Content (Pictures, texts, services, policies, etc.) | 30 | BU QA & GM | Marketing - Quality | N/A
52 | WhatsApp & Fb Messenger for Guest Relations | Supervise execution of the project (SIM card + Byom provider) and assure the hotel guest relations has the WhastApp communication guidelines | 30 | Marketing Director & MKT experience BU | Marketing - Experience | Guidelines
53 | FASTPASS Initiatives: OCO* | Request OCO training for all front desk staff. Order and place Comm. Materials - Marketing BU *OCO implementation only applies if the hotel has the payment gateway implemented. | 30 | Marketing Director / GM | Marketing - Experience IT Business Transformation - S&T | Guidelines / Brand Center
54 | Types of Communication | B2C including NHR: NH Openings Multi Brand: periodic newsletter uniting together recent openings Destination in focus: monthly B2C email, new hotel will be highlighted in the list of hotels of the promoted destination (if city hotel and desitination are the same) B2B: NH Openings Multi Brand: periodic newsletter uniting together recent openings Hotel stand alone nHow brand Hotel stand alone other brands in case of strong business offer or hotel type (e.g. Conference Center). | 23 | Contact Plan Team CRM | CRM & Loyalty | N/A
55 | Analyse the E-mailing Inclusion | - Hotel emailing B2C(uniting recent openings) B2C - Hotel featured in special Destination email B2C (if applies) - Hotel emailing B2B (standalone or features in global/monthly newsletter) | 23 | Marketing Director | CRM & Loyalty | N/A
56 | Marketing & Brand Positioning Orientation | Marketing and brand positioning orientation (Brand Days in NHC) | 15 | Marketing Director | Marketing - Branding | N/A
57 | Standard Manual Training | Staff training on Operation Standard Manual per brand | 15 | BU QA & GM | Marketing - Quality HHRR - NH University | Standards Manual
58 | Key Principles of Service | Assure that all staff get the online training | 15 | GM | Marketing - Experience | Handbooks
59 | Check Ancillary Projects | Check Ancillary projects available for deployment (e.g. Promotional Packs etc.) | 15 | Marketing Director | Marketing - Experience | N/A
60 | Loyalty Training Plan | Loyalty staff training and support by conference call | 7 | Loyalty Team HQ | CRM & Loyalty Operations | MS Teams
61 | Discovery Loyalty Training Plan | Support on technical procedures | 7 | CRM & Loyalty | CRM & Loyalty Operations | MS Teams
62 | Loyalty Global Agreements | Knowledge of Loyalty Global Agreements. Foster regional partnerships (Alitalia, Iberia Plus, Aeroméxico, Air Europa) | 7 | Loyalty Team HQ & Key User BU | CRM & Loyalty | N/A
63 | Site Inspection (II) | Site inspection focused on standards implementation | 7 | BU QA & GM | Marketing - Quality | N/A
64 | Quality plan review | Carry out the quality plan review | 7 | BU QA & GM | Marketing - Quality | N/A
65 | Activation of the TMS4Loyalty module | Open a Jira to active the TMS4Loyalty module for Loyalty and Frequent Flyer Programs (FFP) | 1 | Loyalty Team HQ | CRM & Loyalty | NH SERVICE DESK (Jira)
66 | Web Topics | Web topics update- Incorporation new Hotels in Loyalty and Frequent Flyers | 1 | Loyalty Team HQ | CRM & Loyalty E-Commerce | N/A
67 | Pictures Information | Generic Hotel photos slideshow Hotel Video (product) Hotel Spherical Photos Google Street VR Sales Kit (spherical photos & videos- HQ Trade Mk Guidelines) Hotel Photo Key Visuals Advertising (Models) Hotel Video Key Visuals Advertising (Models) | 0 | Marketing Director | Marketing - Advertising | Brand Center
68 | Hotel Communication | Feature hotel in Tell the World global newsletter Feature hotel in Desktop Taser global / local | 0 | Marketing Director | Marketing - Internal Communication
69 | Quality Reports Inclusion | Add hotel into all Quality Reports | 0 | HQ QA | Marketing - Quality | N/A
70 | Hotel communication (templates) | Supervise the use of the correct templates for onsite communication | 0 | Marketing Director & MKT experience BU | Marketing - Experience | Brand Center
71 | Digital Signage | Supervise that the correct videos by brand are used, the templates and look&feel is acoording to guidelines, and the use of instagram html is done | 0 | Marketing Director & MKT experience BU | Marketing - Experience | Guidelines
72 | Guest Experience Feed-Back | Guest Experience feed-back (analysis of reviews and comments - Quality Focus, TripAdvisor, Trust you or similar) | 0 | BU Quality responsible | Marketing - Quality | Quality Focus, TripAdvisor, Booking, Expedia, Google, etc.
73 | Hotel Standards Check | Check Hotel Standards after the opening | 15-30 days after Opening | BU QA & GM | Marketing - Quality | Standards Manual
74 | Preferred & Amex Program (if applies) | Share information with Hotels included in these programs and Train them | 60 days after Opening | HQ QA | Marketing - Quality | N/A
75 | Mobile Guest Service | Assure the implementation of the project, hotel training and service billing process | 30 | BU Quality responsible | Marketing - Experience | N/A
76 | Pet project | Assure the implementation of the project, hotel training and the purchase of the materials. Adapt the onsite materials. | 45 | Marketing Director | Marketing - Experience | Standards Manual/Guidelines
77 | City Connection | Assure the hotel training and purchase the onsite material (passport) | 45 | Marketing Director | Marketing - Experience | Standards Manual
78 | VIP treatment | Assure that the hotel has the standard and materials for a correct implementation of the project | 30 | BU Quality responsible | Marketing-Quality | Standards Manual/Guidelines
79 | New Amenities intstallation | Assure that the hotels install the dispensers in the baths | 60/90 | Maintance | PCM&E | Guidelines
80 | Tablets in Reception Installation (if applies) | Once installed the WifiCorp and the new priting machines, assure the hotel is in the scope of the project. If this project applies, assure the trainning and the implementation of the tablets. | 60/90 | IT/Experience/Business Procesess | IT/Experience/Business Procesess | N/A
Business Processes - Operations

## Operations
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task | Task Description | When (days before opening) | Responsible | Departments Involved | Tools
1 | Opening Communication | Receive from Legal department the e-mail with the opening information | Once the contract is signed | Legal Director | All company areas | E-Mail
2 | Legal Documentation | Obtain the legal documentation: Civil Liability Insurance, Fire Certificated, Health and Safety, NH Outdoor Signage Permits, Opening & Activity Licences, Tourism License, All Guarantees, Built Project, Diligence in case of refurbishment, Other Legal requirements (carpet, FR Doors, False Ceiling, …) | Depends on the country and type of contract and permits | General Manager & Project Manager | Operations - GM PCM&E Legal | N/A
3 | Hotel registration in Tourism Administration | Hotel registration in Tourism Administration | Depends on the country and type of contract and permits | General Manager | Operations - GM Legal | N/A
4 | PreOpening Team & Communication | Proceed with the The PreOpening Team process. See the "PreOpening Team Template" tab on the same document. | 365 | Operations Director BU | Operations | PreOpening Team Template
5 | Opening Budget | Prepare pre opening budget | 180 | General Manager | Operations - GM | N/A
6 | Personnel Hiring (I) | General Manager Position Hired | 180 | Regional Operations | Operations - GM HHRR | N/A
7 | Suppliers | Negotiate supply, cleaning and collection of linen/towelling and uniforms with external laundry operator | 150 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
8 | Airport Signs | Check into requirement of airport signs. (IF APPLICABLE) | 120 | General Manager | Operations - GM | N/A
9 | Lanyon | Lanyon complementation + add. Information sheet | 120 | General Manager & Regional Director of Sales & Revenue Manager | Operations - GM | N/A
10 | Environmental sustainability | Take legal and compulsory Environmental measures and actions related with Environmental sustainability that should be consider during the preopening of a Hotel within the NH Hotel Group. | 120 | General Manager | Operations - GM | Guide of environmental procedures
11 | Sales Activation | Confirm sales activation date, open availability/house status | 120 | General Manager & Regional Operations & Revenue Manager | Operations Commercial - Sales | TMS4H, NHWeb
12 | Equipment | Room equipment product quality of linen, towels, pillows, etc. | 120 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
13 | Licenses | Check all licenses that are to be posted in the hotel: Signage, Hotel, Restaurant, Liquor, Entertainment, Shops, Vitrines, License SAT & Cable TV, Ford… | 90 | General Manager & Project Manager | Operations - GM | N/A
14 | Equipment | Define with Operation departments the equipment needed | 90 | General Manager | Operations - GM | N/A
15 | Deliveries Schedule | Completion of full planning of deliveries coordinated with project and building department. | 90 | General Manager | Operations - GM PCM&E | N/A
16 | Virtual Planner Tool | Evaluate implantation of Virtual Planner Tool (Applicable if M&E hotel) | 90 | General Manager | Operations - GM | Virtual Planner Tool
17 | Induction Program Inclusion | Define if the induction program is needed (for GM, HOD, staff…) | 90 | General Manager | Operations - GM | N/A
18 | Personnel Hiring (II) | Start with the Head Of Departments Position Hiring Process | 90 | General Manager & Maintenance Regional | Operations - GM HHRR | N/A
19 | Define a Key User | - Define a Key User as first and provisional purchasing responsible until the employees of the hotel will be hired - Grant access permission to the Key User | 90 | S&T MM | Business Transformation - S&T | N/A
20 | Personnel Purchasing | Define the structure in the hotel who is going to place orders/receptions/inventory | 90 | GM & Operations & HHRR | Operations HHRR | N/A
21 | Orders (I) | Order the materials that ensure compliance with the standards of the Brand, paying special attention to this materials: Uniforms (if the employees are not hired yet, possibility to make a size standard order). Linen and room clothes. Amenities. | 90 | Key User | Business Transformation - S&T | TMS4MM
22 | Suppliers | Cleaning of refurbishment works, decide Who will do it? Negotiate with external company, glaziers, polishers, etc. | 90 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
23 | Material | Define operative material | 90 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
24 | Furniture List / List of Endowment | Prepare a list with all the furniture and elements of the rooms | 90 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
25 | Action Plan | Set up action plan for linen and uniforms | 90 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
26 | Cleaning Products Order | Order the cleaning products needed | 75 | Housekeeping Manager & Houseware & General Manager | Operations - Housekeeping PtP | N/A
27 | Linen Department Operative | Linen department: determine routing, quantities, stock and distribution | 75 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
28 | Personnel Hiring (III) | Start with the Rest of Employees Position Hiring Process | 60 | General Manager | Operations - GM HHRR | N/A
29 | General Customising Sheets | Send out to S&T team the customising sheets fulfilled in order to configurate the hotel system (General Info, Inventory, SAP Access, TMS Employees, Minibar, Housekeeping, Maintenance, Room Features…) | 60 | Front Office Manager | Operations - Front Desk IT Applications Business Transformation - S&T | E-Mail
30 | FASTPASS Initiatives: OCI & CYR | Open a Jira in the category "Front Office" and subcategory "Online check in - Choose your room" uploading the floor plans and features for OCI / CYR | 60 | General Manager | Operations - GM IT Applications Business Transformation - S&T | NH SERVICE DESK (Jira)
31 | Opening Communication | Inform the opening to the necessary official estates | 60 | General Manager | Operations - GM | N/A
32 | Signage List | Prepare control list on hard standards (Signage list) | 60 | General Manager | Operations - GM | N/A
33 | Local Hotel School Relationship | Establish local hotel school relationship | 60 | General Manager | Operations - GM | N/A
34 | OTA's and Metasearch Access | Register hotel in TripAdvisor, Booking, Expedia, Google… | 60 | Front Office Manager & General Manager | Operations - Front Desk | TripAdvisor, Booking, Expedia, Google, etc.
35 | Cleaning Programme | Start cleaning programme all hotel facilities (front and back of the house) | 60 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
36 | Laundry Operative | Define the laundry operative with schedules and shifts | 60 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
37 | Department Operative | Define the operative department with personnel, time schedules, shifts, cleaning areas, lost&found items… | 60 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
38 | M&E Areas Operative | M&E: operational design, equipment, quantity, different set-up and content, recommended capacities, etc. | 60 | F&B Manager & General Manager | Operations - F&B | N/A
39 | Kitchen Area Operative | Kitchen: operational design (assignment and organization of stores/refrigerator), utensils requirement, etc. | 60 | Chef Manager & General Manager | Operations - F&B | N/A
40 | Outlets F&B Operative | Outlets F&B (bar, breakfast, restaurant, terrace...): operational design, equipment, quantity, recommended capacities, etc. | 60 | F&B Manager & General Manager | Operations - F&B | N/A
41 | Legal Traffic Regulations | Legal traffic regulations (merchandise, production and cleaning) | 60 | Houseware & F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
42 | List of All Corporate Printing Requirements | Prepare list of all corporate printing requirements: hotel logo, letter, type, menus, M&E, etc. | 60 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
43 | Chinaware Requirements | Prepare chinaware requirements: typology, quantities and budget | 60 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
44 | General Customising Sheets | Send out to FO Manager/General Manager the customising sheets for its fulfilment. Once received from the hotel, proceed with IT department with the configuration (General Info, Inventory, SAP Access, TMS Employees, Minibar, Housekeeping, Maintenance, Room Features…) | 60 | Support & Training Team | Business Transformation - S&T IT - Infosec Operations - FOM | Hotel Opening General Customising
45 | [5 empty] | Hotel Opening Meetings Customising
46 | Insurances | Assure that all the insurance are signed: loss and stocks, fire, flood, car park, civil disorder, theft and damage to guest property, workers... | 45 | General Manager & Project Manager | Operations - GM | N/A
47 | Building Management | Check on outside cleaning, garbage collection, waste management, schedule of hotel equipment… | 45 | General Manager | Operations - GM | N/A
48 | Task Force | Prepare a list of approved facilities for personnel to stay during start up period for Taskforce & Trainees | 45 | Regional Director Operations | Operations - GM | N/A
49 | Task Force | Prepare Taskforce schedule (15 days before and after the opening) and determine number of participants | 45 | General Manager | Operations - GM | N/A
50 | Masterkeys | Masterkeys control list. Assure draft authority levels for use masterkeys. | 45 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
51 | Stewards Area | Stewards: operational design, utensils, etc. | 45 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
52 | M&E Strategy | M&E: establish cost/price sales program of gastronomic offer (scandal, pricing), market positioning, etc. | 45 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
53 | F&B Strategy | F&B: establish cost/price sales program of gastronomic offer (scandal, pricing), market positioning, etc. | 45 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
54 | HACCP | - Sanitary authorization - Implementation, contact local provider (BU) - Control files on site - Check food handler certificate for kitchen & restaurant staff - Plague control | 45 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
55 | Staff Requirement by Season | Describe staffing level requirement by season | 45 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
56 | SAP Access | Ensure that all the SAP access are working properly and verify that staff SAP profile are the correct ones | 30 | General Manager | Operations - GM | N/A
57 | Opening Progress Chart | Prepare opening progress chart to be posted near staff entrance. Schedule available rooms / area’s pre-opening. | 30 | General Manager | Operations - GM | N/A
58 | Schedule PreOpening | Distribute schedule to Heads of dpt. for rooms/area’s pre-opening to align the organization of all departments | 30 | General Manager | Operations - GM | N/A
59 | Storages Areas Distribution | Check departmental storages areas to be operational | 30 | General Manager | Operations - GM | N/A
60 | Temporary Office Facilities | Agree temporary warehouse facilities pre-opening period. (if needed) | 30 | General Manager | Operations - GM | N/A
61 | Site Inspections, Tours | Organise familiarisation tour for groups, potential local and national clients. Site inspections | 30 | General Manager & Regional Director of Sales & Revenue Manager | Operations - GM | N/A
62 | HOD Organization | Establish Head Of Departments meetings, organization and staffing chart | 30 | General Manager | Operations - GM | N/A
63 | Collective Labour Agreement | Inform new staff on Collective Labour Agreement applicable and ensure all employees are familiar with the various hotel policies regarding payment date, sick leave, vacation, social benefits. | 30 | General Manager | Operations - GM HHRR | N/A
64 | Operative | Review the operative and procedures with the rest of departments | 30 | General Manager | Operations - GM | N/A
65 | User Access Codes Configuration | Request to IT the user access codes or modify the current ones according to the employee´s needs (Permissions) | 30 | Support & Training Team | Business Transformation - S&T IT - Infosec | NH SERVICE DESK (Jira)
66 | Training Planning | Define a training plan for the new employees of FO, F&B, Sales, Housekeeping and MM departments. | 30 | Support & Training Team | Business Transformation - S&T HHRR | N/A
67 | Construction Contact List | Compilation list of telephones and contact persons of the different offices that have intervened in the construction of the Hotel | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
68 | Facilities Inspection | Inspection of the facilities before the works are completed and send the report to Operations, PCM&E and Assets if deficiencies have been detected | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
69 | Snagging List | Weekly deliver the damage sheet, pending issues or detected refurbishment defects to the project responsible. Update and follow up is mandatory | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
70 | Characteristics of the Installed Equipment | Realization of the technical report with the characteristics of the installed equipment (pumps, boilers, etc. ...) | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
71 | Operation Manuals | Elaborate operation manuals and training (if apply) of the equipment to the different departments of the hotel: fire central switchboard, loudspeaker system, lighting… | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
72 | Contracts | Control and monitoring of the basic services contracts of the Hotel: water, electricity, telephone, fax, gas, garden, grounds, background music, waste management, license SAT & Cable TV, bacteorostathic, disinfection, decontamination and rat control ... | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
73 | Facilities Plans | Request facilities plans: Telephony, data, electricity, hot water, accumulators, heat exchangers, boiler, plumbing (cutting keys), air conditioning, etc. | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
74 | Consumption Register | Implement consumption register with daily reading of water, light, gas and temperatures | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
75 | Project endorsement | Project endorsement facilities: gas, electricity, air conditioning, swimming pools, plumbing, telecommunications, fire, etc... | 30 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
76 | Equipment | Acquisition of maintenance equipment (tool, epis, workshop furniture, spare parts, etc.) | 30 | General Manager & Maintenance Regional | Operations - Maintenance | N/A
77 | Training Maintenance | Maintenance will receive specific training by the installers of the hotel, where they will explain all the operation of the hotel facilities. | 30 | General Manager & Maintenance Regional | Operations - Maintenance Human Resources | N/A
78 | Emergency Evacuation | Emergency evacuation procedure and simulate emergency situation with all hotel employees | 30 | General Manager | Operations - GM PRL | N/A
79 | Special guest conditions | Determine VIP, regular and long staying guest criteria and policy | 30 | Regional Director of Sales & General Manager | Sales - Actions | N/A
80 | Hotel Positioning | Complete hotel positioning, get approval from DBD | 30 | General Manager | Sales Operations | N/A
81 | Hotel Services Directory | Prepare contents of hotel services directory | 30 | Front Office Manager & General Manager | Operations - Front Desk | N/A
82 | Hotel Maps | Require the hotel maps with square meters to manage the cleanliness properly | 30 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
83 | Procedures | Implement procedures: lost and found items, cleanliness of the rooms... | 30 | Housekeeping Manager & General Manager | Operations - Housekeeping | NH Digital Knowledge Workplace
84 | Training Housekeeping | Training room attendants | 30 | Housekeeping Manager & General Manager | Operations - Housekeeping | N/A
85 | Initial Supplies List | Review the initial supplies list | 30 | F&B Manager & Chef Manager & General Manager | Operations - F&B Coperama | N/A
86 | Par-stock Requirements | Prepare par-stock requirements by quantities for food & general supplies. Calculation of purchase by volume of warehouses | 30 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
87 | Machinery | Machinery review performance | 30 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
88 | Working Schedules | Establish working schedules and set a minimum & maximum staff for outlet (hour work) | 30 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
89 | TV Branded Content | Implementation of Smart Install server to upload all hotel information to TV rooms (Directory, videos, brand information ...) If applicable | 20 | Marketing Director | Operations - Maintenance Marketing PCM&E | N/A
90 | Telephone Numbers Configuration | Set up telephone number system for rooms/services | 20 | Front Office Manager & General Manager | Operations - Front Desk PCM&E | N/A
91 | Supplier & Materials analysis | Analyse the needed suppliers to guarantee the hotel's operations mainly based in nominated vendors (priority) and in the standards defined by the company. In the case of there is no nominated vendor that meets this need, request to PtP the creation of non nominated vendor through SAP. | 20 | Operations | PtP Operations | N/A
92 | Training MM | Receive the TMS4MM Training Plan for new employees. (If apply) based in check list for trainings | 20 | S&T MM | Business Transformation - S&T | N/A
93 | Deliveries Schedule (II) | Check the delivery schedules for the operations of the suppliers | 15 | Hotel MM User | Operations | N/A
94 | Orders (II) | - Orders to guarantee the hotel's daily operations - Orders of maintenance contracts | 15 | Hotel MM User | Operations | N/A
95 | Health Services | Legionella and analytical control book. Relevant health services. | 15 | Maintenance Manager & General Manager | Coperama Operations | N/A
96 | General Requirements | Check Uniforms, Identification plates, Tools, Complaints and Claims forms and Personal Protection Equipment | 15 | General Manager | Operations - GM | N/A
97 | Contract List | Summary report of all maintenance contracts to be available for the hotel departments: company name, phone, contact, support schedule (24 x7,…), etc. | 15 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
98 | Facilities Maintenance | Regulations for preventive, daily, weekly and monthly maintenance of hotel facilities | 15 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
99 | TV Configuration | TV Inspection and definition of the TV channels, parabolic, Canal + | 15 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
100 | Telephone Hotel List | Testing telephone extensions, benchmarks, SAI, etc.. | 15 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
101 | Suppliers Maintenance | Check the maintenance suppliers: Ironmongery, electrical equipment, plumbing, equipment, etc. | 15 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
102 | Certificates | Quality certificates of all installed equipment | 15 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
103 | Health Services | Legionella and analytical control book. Relevant health services. | 15 | Maintenance Manager & General Manager | Operations - Maintenance | N/A
104 | Legal Documentation | Facilities legal documentation (medium voltage, low voltage, elevators, fires, Legionella, etc.) and the regional maintenance manager directs the maintenance manager, before the hotel opens. | 15 | General Manager & Maintenance Regional | Operations - Maintenance | N/A
105 | Site Inspection | Site Inspection training to the team | 15 | Regional Director of Sales & General Manager | Sales - Actions | N/A
106 | Task Force | Elaborate a list with all the TaskForce&Trainees data and their room number in order to everybody knows where they are acommodating without the SAP system activated. | 15 | Front Office Manager & General Manager | Operations - Front Desk | N/A
107 | Training Front Office | The Front Office will receive a general training: Corporate Training, System and Processes, Quality and Standards Brand, Health and Safety… | 15 | Front Office Manager & General Manager NHUniversity Business Transformation - S&T | Operations - Front Desk HHRR - NH University | NH Digital Knowledge Workplace NH Talent - Learning
108 | Employees Canteen | Prepare, decide cost pricing and agree meal programme for employees canteen | 15 | F&B Manager & General Manager | Operations - F&B | N/A
109 | Check-List | Elaborate a check list with the open-service-close shifts | 15 | F&B Manager & Chef Manager & General Manager | Operations - F&B | N/A
110 | Cleaning Responsibilities | Agree cleaning responsibilities between F&B and Housekeeping | 15 | F&B Manager & Chef Manager & Housekeeping Manager & General Manager | Operations - F&B | N/A
111 | Rates, Availability and Prepayments | Check the content in the system: rates, availability, pending prepayments... | 10 | Front Office Manager & General Manager | Operations - Front Desk | SAP_TMS
112 | Training POS | Employee training: - Presentation of the gastronomic offer - NH Standards - TMS4POS | 10 | F&B Manager & Chef Manager & General Manager | Operations - F&B HHRR - University | Standards Manual
113 | Guest Literature | Check on operating forms and guest literature ordered. | 7 | Front Office Manager & General Manager | Operations - Front Desk | N/A
114 | Information City Folder | City maps and develop the Hotel / City information folder for the client | 7 | Front Office Manager & General Manager | Operations - Front Desk | N/A
115 | Support Planning | Support on the spot after the migration (during one month) | 0 | Support & Training Team | Business Transformation - S&T | N/A
Business Processes - Operations

## Finance
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task |  | When (days before opening) | Responsible | Departments Involved | Tools
1 | Opening Communication | Receive from Legal department the e-mail with the signed contract confirmation | Once the contract is signed | Legal Director | All company areas | E-Mail
2 | Cash Flow Forecast Inclusion | Monthly BU cash flow forecast inclusion | Once the opening hotel information is known | Treasury Director BU | Treasury | Kyriba
3 | MD Company_Center Template | Open a JIRA Ticket and attach the "BUD17 Template for new hotels" template: - Onyx Model Inclusion in order to pay all commission invoices - Shared Services Center Inclusion - PO/BOX or email address to send the invoices. - SAP MM Inclusion - Automatic Approval Flow - Purchasing Organization (PO) and Purchasing Organization Reference (POR) - Suppliers Migration (Extension/Initial Load/NO). - Source Company to extend Suppliers - F&B Volume - Electronic invoicing in order to create an operation point to suppliers Electronic Digital Invoicing (GLN Number) - etc. | 365 | Administration Director BU | Administration IT - Applications | BUD17 Template for new hotels NH SERVICE DESK (Jira)
4 | Deposit mangement | Deposit mangement if applicable | 365 | Treasury Director HQ | Treasury | N/A
5 | Guarantee bank management | Guarantee bank management if applicable | 365 | Treasury Director HQ | Treasury | N/A
6 | MD Company_Center Template | MD Company_Center, include the new center and company and share with all financial directors and Share Service Center, the updated information. | 360 | Administration Director BU | Administration | Excel / E-Mail
7 | New Bank Account | Request new bank account to the bank and inform HQ | 200 | Treasury Director HQ | Treasury | N/A
8 | Supplier and Materials Extension | Inform to IT department which suppliers and materials must be extended | 180 | HQ PtP | HQ PtP IT | N/A
9 | Supplier and Materials Copy | Proceed with the copy of CAPEX & OPEX suppliers and materials | 180 | HQ PtP | HQ PtP | N/A
10 | Sign Contracts with Credit Cards | Sign contracts with credit cards (Amex, Diner, Elavon) | 150 | Treasury Director HQ | Treasury | N/A
11 | Account in Kyriba | Create the bank account in Kyriba and request to IT the creation in SAP | 150 | Treasury Director HQ | Treasury | NH SERVICE DESK (Jira)
61 | General Information | Inform the E-Commerce Team about tax treatment (both VAT and city tax if applies) | 130 | E-Commerce Manager BU & Tax Director BU | Taxes Marketing - E-Commerce | N/A
62 | General Information | Inform E-Commerce Team about data for online payments (Amex and Elavon E-commerce Web MIDs) | 130 | Treasury HQ | E-Commerce Finances - Treasury | N/A
12 | Adyen Merchant | Send to E-commerce credit cards and bank account information to open Adyen merchant. Send the access to the hotel. (When applicable) | 130 | Treasury Director HQ | Treasury | E-Mail
13 | New Hotel Communication | Inform to the suppliers about the new hotel | 90 | Coperama | Coperama | N/A
14 | Onyx Model | If the hotel will be included in the Onyx model, inform ONYX | 60 | AR Administration Process Lead HQ | Administration | Onyx Interface
15 | Credit Card Terminal Request | Request Credit Card Terminal to the bank and Gateway | 45 | Treasury Director HQ | Treasury | Terminal Request Process
16 | Cash Float Assignation | Assign together with operation the "Float" of the reception/bar | 45 | Treasury Director BU | Treasury Operations - GM | N/A
17 | SAP Training Plan | If the hotel is management contract and NH will not manage the accountancy, receive SAP Training Plan. For owned/lease hotels, training requirements for GM (i.e.: P&L and aging reports). Training should include BPC Forecast/Budget process. | 30 | Administration Director | Administration | SAP_FI
18 | New PO BOX Request | If the hotels is a new company and will be managed by Share Service Center, it is needed to request a New PO BOX to manage all invoices from Suppliers | 30 | AP Administration Process Lead | Administration | N/A
19 | DFM Inclusion | Include the new hotel in DFM/DWP. Send the access to the hotel. | 30 | Administration Director | Administration | DFM/DWP
20 | SAP Access Permissions | Request/assign the correct SAP access for users to include the new center/company in the roll | 30 | Administration Director | Administration IT - Infosec | NH SERVICE DESK (Jira)
21 | Exchange Authorization | Request to national bank authorization to do Exchange rate in the hotel (If applicable) | 30 | Treasury Director BU | Treasury Operations - Front Desk | Official Request
22 | Management Fee Calculation | Read and review management contract, to calculate management fee etc. | 20 | BU Finance Director | Administration | N/A
23 | AR Inclusion | Include the new hotel to the electronic invoicing tools for Accounts Receivable (Voxel, Edicom) | 20 | AR Administration Process Lead | Administration | Voxel, Edicom
24 | Building Information | Receive the information about the square meters built in the different areas of the hotel. | 15 | Project Manager & General Manager | Taxes PCM&E | N/A
25 | Local Taxes Applicable | Settings the local taxes applicable for the hotel (i.e.: Property Tax, Rubbish Tax, City tax etc.) | 15 | Treasury Director BU | Taxes Operations - GM | N/A
26 | Load of suppliers and materials (II) | Proceed to load the suppliers and materials missed. | 15 | PtP | PtP | TMS4MM
27 | VAT report to Tax Authorities | Decide if the hotel will be included in the " telematic system for tax information remittance " (if applicable), using our IT system. | 15 | Tax Director / Administration Director | Taxes | N/A
28 | Access Liability, Building, Fire Insurances | Request to the Insurance Broker the inclusion of the hotel in the insurance programs, declaring values to be insured | 10 | BU Finance Director & admin responsible | Treasury | N/A
Business Processes - Operations

## IT
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task | Task Description | When (days before opening) | Responsible | Departments Involved | Tools
1 | Opening Communication | Receive from Legal department the e-mail with the signed contract confirmation | Once the contract is signed | Legal Director | All company areas | E-Mail
2 | User Access Codes Configuraction | Create user access codes or modify the current ones according to the employee´s needs (Permissions) | As soon as the employees are hired | Infosec | Infosec Operations - S&T | N/A
3 | WIFI Installation | WIFI: Accept budget and install all devices | 90 (depends on egineering) | Fractalia & Hoist | Infrastructure | N/A
4 | Company & Center | Creation of Company Code and Business Area. Set-up the Global Local Number of the Hotel . Once the process is finished, inform to Administration department. | 360 | IT BackOffice Manager | Applications | SAP ERP
5 | P2P Portal activation | P2P Portal activation | 300 | IT BackOffice Manager | Applications | SAP MM / B2B Portal
6 | Hyperion configuration | Hyperion configuration | 300 | IT BackOffice Manager | Applications | Hyperion
7 | BPC configuration | BPC configuration | 300 | IT BackOffice Manager | Applications | SAP.BPC
8 | Kyriba configuration | Kyriba configuration | 300 | IT BackOffice Manager | Applications | Kyriba
9 | Legal requirements for using applications | Country/region legal requirements when hotel opening in country or region where NH is not using corporate applications yet. | 180 | BU Directors | Applications | N/A
10 | New Line Comms. | Comm.: Need the detailed address to request the optical fiber to provider | 180 | Telefonica | Infrastructure Communication | N/A
11 | Order New Line | Comm.:Order Corporate data lines (Telefonica) via HQ Madrid | 180 | Telefonica | Infrastructure Communication | N/A
12 | Mail Accounts (I) | Creation/Activation of the generic hotel email account | 180 | Infrastructure Manager | Infraestructure | Outlook
13 | Operations send inventory to IT | Inventory of positions in the hotel: FO, BO, Sales, GM, etc. | 120 | Operations | Infrastructure | N/A
14 | WIFI Request | WIFI: request to provider a site survey | 120 | Fractalia & Hoist | Infrastructure | N/A
15 | Taxes and VAT | List of applicable taxes and VAT | 120 | HQ Admon Process Leads | Applications Administration | SAP _SD & TMS4H
16 | Type of billing documents | List of applicable type of billing documents | 120 | HQ Admon Process Leads | Applications Administration | SAP _SD & TMS4H
17 | Clients copy/extension | Clients copy/extension (Internal, payment methods, CPD, generic) | 120 | HQ Admon Process Leads | Applications Administration | SAP _SD & TMS4H
18 | Hotel Structure | Hotel structure creation (buildings, rooms, meeting rooms) | 120 | BU Operations Director | Applications | TMS
19 | TMS4C channels setup | TMS for Connectivity channels set-up. | 120 | HQ DCM Director | Applications | TMS4C
20 | Communication | Inform to Revenue and CDM that the system is ready for external clients copy, rate creation, contracts extension and sales strategy creation | 120 | IT FrontOffice Manager | Applications Revenue CDM | E-mail
21 | Request Device | Request to provider all devices: Computers, Switches, Ups and Servers | 100 | HP & Infrastructure Manager | Infrastructure | N/A
22 | Request Device | Request to provider all printers or fiscal printers | 100 | Ricoh & Others | Infrastructure | N/A
23 | Request Device | Request to provider POS printers | 100 | Local Poovider | Infrastructure | N/A
24 | Request Device | Request Business Center (If apply) | 100 | Econocom & Hoist & Fractalia | Infrastructure | N/A
25 | Request Device | Device for payment gateway | 100 | 3C | Infrastructure Treasury | N/A
26 | Install New Line | Comm.: Prepare all connectivity such as Tel data lines, Wifi etc. | 90 | Telefonica | Infrastructure Communication | N/A
27 | Mail Accounts (II) | Creation/Activation of the generic departments email accounts | 60 | Infrastructure Manager | Infraestructure | Outlook
28 | Mail Accounts (III) | Creation/Activation of the nominative email accounts | once the personnel is hired | Infrastructure Manager | Infraestructure | Outlook
29 | GL accounts coding for TMS mealplan concepts | General Ledger accounts coding for TMS mealplan concepts (Room Only, Bed & Breakfast, Half Board, Full Board, All Inclusive) | 30 | HQ Admon Process Leads | Applications Administration | SAP FI
30 | Cost centers coding for TMS mealplan concepts | Cost centers coding for TMS mealplan concepts (Room Only, Bed & Breakfast, Half Board, Full Board, All Inclusive) | 30 | HQ Admon Process Leads | Applications Administration | SAP FI
31 | PA module adaptation | PA module adaptation when hotel is located in a new country | 30 | IT HR Manager | Applications | SAP HCM
32 | Setup NH | Setup and configure all devices (need the line working) | 20 | Infrastructure Manager | Infrastructure | N/A
33 | Interface | Install all interfaces | 20 | Infrastructure Manager | Infrastructure | N/A
34 | Communication | Communicate PtP, Administration and CDM departments that the system is ready for clients, providers (external & internal), contracts, and materials extensions | 15 | IT BackOffice Manager | Applications | E-Mail
35 | SAP IM set-up | Investmen Management set-up | 15 | IT BackOffice Manager | Applications | SAP IM
36 | Click&Hire setup | Click&Hire setup | 15 | IT HR Manager | Applications | SAP HCM
37 | Work center structures set up | Work center structures set up (enterprise, personnel, organizational plan…). | 15 | IT HR Manager | Applications | SAP HCM
38 | Organizational structure creation & personnel upload | Communicate HR dept system is ready for organizational structure creation and personnel upload | 15 | IT HR Manager | Applications Human Resources | E-Mail
39 | Complete set up | Complete set up of: Concepts, templates (invoices, tickets, Welcome cards,…), Tills, hotel employees, Housekeeping, POS structure, Events structure, Electronic invoicing | 7 | IT FrontOffice Manager | Applications | TMS
40 | TMS4P activation | TMS for Pay activation | 7 | IT FrontOffice Manager | Applications | TMS4P
41 | NH Talent activation | Success Factors interface activation | 7 | IT HR Manager | Applications | NH Talent
42 | Local Payroll system interface activation | Local Payroll system interface activation | 7 | IT HR Manager | Applications | N/A
43 | TMS for Loyalty setup | TMS for Loyalty setup | 7 | HQ MK Process Lead | Applications | TMS4L
Business Processes - Operations

## PCM&E
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task | Task Description | When (days before opening) | Responsible | Departments Involved | Tools
1 | Opening Communication | Receive from Legal department the e-mail with the signed contract confirmation | Once the contract is signed | Legal Director | All company areas | E-Mail
2 | Legal Documentation | Obtain the legal documentation: Civil Liability Insurance, Health and Safety, NH Outdoor Signage Permits, Opening & Activity Licences, Tourism License, All Guarantees, Built Project, Diligence in case of refurbishment, Other Legal requirements (carpet, FR Doors, False Ceiling, …) including fire certificates | Depends on the country and type of contract and permits | Project Manager | PCM&E Operations Legal | N/A
3 | Materials and Suppliers loading | Check the loading of materials and suppliers | 300 | Capex controller & Project Manager | PCM&E PtP | N/A
4 | Renders Creation | Deliver renders or/and pictures | 180 | Project Manager | PCM&E | N/A
5 | Hiring & Training | Maintenance Manager must be hired and must receive the SAP Training Plan (If apply) | 180 | Regional Manager Engineering & Maintenance Manager & General Manager | PCM&E Operations HHRR | N/A
6 | Materials & Equipment | Check quantities and delivery times of materials and equipment. | 180 | Project Manager & Operations | PCM&E Operations | N/A
7 | Supplier Contracts | Electricity, Gas, Water, Telephone Switchboard, Other (district heating, district cooling …) | 120 | Regional Manager Engineering & Maintenance Manager & IT | PCM&E IT | N/A
8 | Define the Supply and Maintenance Contracts | Ask through SAP system the creation or extension of the supply and maintenance contracts signed by the hotel in order to upload the vendors and materials related to these contracts in SAP. | 90 | Project Manager & Regional Manager Engineering & Maintenance Manager & Operations | PCM&E PtP | N/A
9 | Protocols of All Installations (I) | Developer's test protocols of all installations | 90 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
10 | Protocols of All Installations (II) | Commissioning and Start Up Protocols of all installations | 90 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
11 | Initial Technical Audit | Technical audit of the hand out of installations | 90 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
12 | Water Check | Check water containing plan\cleaning filters and set up legionella control procedures. | 90 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
13 | Elevators Operational | Verify elevators operational-check contract because of heavy duty use during construction | 90 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
14 | Working Schedules for Equipment | Establish working schedules for equipment | 90 | Project Manager | PCM&E | N/A
15 | CMMS System Implementation | Implementation of the Computerized Maintenance Management System | 90 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
16 | Certifications, technical and legal requirements | Boilers technical room, Fire Protection, Garage, HV Facilities, HVAC/Hot Water, Lifts, LV Facilities, Other Installations, Plumbing Installation, Wastewater Discharge Point, Swimming Pool/Spa. Certifications, technical and legal requirements according to local regulation. | 90 | Project Manager & Regional Manager Engineering & Maintenance Manager | PCM&E Legal | N/A
17 | Maintenance Contracts | Automatic Doors, BMS, Boilers, CMMS System, Drainage, Electronic Locks, Fire Prevention, Freezing Warehouse Kitchen, Gas, Generator, High Voltage, HVAC, Kitchen Hood, Legionella, Lifts, Lightning Rod, Low Voltage, Potability, Telephone Switchboard, Water Treatment, Other Maintenance Contracts | 90 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
18 | Building and Installation Snagging List | Hotel guest room and facilities site inspection review prior to the completion of works (Delivery of minutes to Operations, P&B and owner if deficiencies were detected) Snagging list | 70 | Project Manager & Regional Manager Engineering & Maintenance Manager & Operations | PCM&E Operations | N/A
19 | Internal test Systems or Equipment | Internal test and verification of systems or equipment: plumbing/sewage, air conditioning/heating, electrical/mechanical... | 70 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
20 | Quality of All Installed Equipment | Certificates of quality of all installed equipment (not ff&E) | 70 | Project Manager & Regional Manager Engineering & Maintenance Manager & Operations | PCM&E Operations | N/A
21 | Drawings of All Installations | Get a copy of Drawings of all installations: Telephony, data, electricity, hot water, accumulators, exchangers, boiler, plumbing (heater keys), air conditioning, etc. As built drawings | 60 | Regional Manager Engineering & Project Manager | PCM&E Operations | N/A
22 | Internal Manuals & Guidelines of Equipment Operation | Develop internal manuals and guidelines of equipment operation for the different Hotel departments: fire control panel, PA system, elevators, lighting, etc. | 60 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
23 | Maintenance workshop | Prepare maintenance workshop. | 60 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
24 | Local Maintenance Suppliers | List of local maintenance suppliers (Joinery, electrician material, plumbering, ironmongery, …) | 30 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
25 | Supplier Contact List | Follow up of supplier contact list | 30 | Project Manager & Regional Manager Engineering & Maintenance Manager & Operations | PCM&E Operations | N/A
26 | Consumption Reporting | Incorporate hotel to consumption reporting | 30 | Regional Manager Engineering & Maintenance Manager | PCM&E | N/A
27 | Installations & Facilities Check List | Installations/Facilities check list to do preventive and corrective maintenance: daily, weekly, monthly (Physical & CMMS) | 30 | Regional Manager Engineering and Maintenance & Maintenance Manager | PCM&E | N/A
28 | Recording of Consumption Implementation | Automatic Doors, BMS, Boilers, CMMS System, Drainage, Electronic Locks, Fire Prevention, Freezing Warehouse Kitchen, Gas, Generator, Electricity, HVAC, Kitchen Hood, Legionella, Lifts, Lightning Rod, Potability, Telephone Switchboard, Water | 30 | Regional Manager Engineering and Maintenance & Maintenance Manager | PCM&E | N/A
29 | Equipment List | Complete the list of all equipment manufacturers and suppliers. (Physical & CMMS) | 15 | Project Manager & Regional Manager Engineering & Maintenance Manager & Operations | PCM&E Operations | N/A
30 | FF&E Snagging List | Review Furniture, Fixtures & Equipment as per hotel contract | 15 | Project Manager | PCM&E | N/A
31 | Building Information | Inform to taxes department about the square meters built in the different areas of the hotel | 15 | Project Manager | PCM&E Finances - Taxes | N/A
32 | Installation and Equipment Manuals | Installation and Equipment Manuals | 15 | Project Manager & Regional Manager Engineering & Maintenance Manager | PCM&E Operations | N/A
Business Processes - Operations

## Human Resources
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task | Task Description | When (days before opening) | Responsible | Departments Involved | Tools
1 | Opening Communication | Receive from Legal department the e-mail with the signed contract confirmation | Once the contract is signed | Legal Director | All company areas | E-Mail
2 | Recruitment | Recruitment of the GM position | 180 | Director of People & Director of Operations | HHRR | NH Careers & external recruitment sources (webs, headhunter, SM)
3 | Recruitment | Define and recruit an internal Task Force Team | 180 - 90 | General Manager & Talent Acquisition Area | HHRR | Nh careers
4 | GM Induction Program | GM Induction Program. Including induction in CS | 90 | Operations & Talent Acquisition Area | HHRR | N/A
5 | Recruitment | Define Recruitment Process: Establish path and schedule for hiring all the positions in the hotel, defining job descriptions, sources and resources | 90 | General Manager & Operations & Talent Acquisition Area | HHRR | N/A
6 | Salary Scales | Establish manning guide with salary scales and hotel organizational Chart | 90 | Payroll Manager | HHRR Operations if apply | N/A
7 | Recruitment | Recruitment and selection of the positions as per the schedule defined | 90 - 7 | General Manager & Talent Acquisition Area | HHRR | NH Carees, external recruitment sources (webs, schools, SM), assessment center, recruitment event, etc.
8 | Welcome Kit | Supervise and prepare the "Welcome Kit": corporate brochure, USB Pen with relevant information for the new employee, notebook | 90 - 0 | General Manager & Talent Acquisition Area | HHRR Operations | Welcome Kit materials NH Talent - Learning
9 | External Prevention Service Registration | Register the work center in the external prevention service contract. | Once the employees start with the operative | Health and safety manager & General Manager | HHRR | N/A
10 | Risk Assessment | Preparing the hotel's initial risk assessment | Once the employees start with the operative | Health and safety manager & External prevention service & Internal prevention service | HHRR Operations | N/A
11 | Risks & Measures Information | Ensure that it is inform the employees about the risks and measures existing in their job positions. | Once the employees are registered | General Manager & Head Of Department | HHRR Operations | H&S management software tool (in the countries where it is available)
12 | H&S Training | Ensure that it is accomplishment of the training in labour risk prevention. | Once the employees are registered | General Manager & Head Of Department | HHRR Operations | NH Talent or others
13 | Training Plan | Identify training areas and prepare training calendar (incl. onboarding, statutory, coperate , hotel and departamental training) | 60 | University department | HHRR | NH Talent and/or others
14 | Emergency & Self-Protection Plan | Preparation of the Emergency and Self-protection Plan of the hotel. | 30 | Health and safety manager & General Manager & External provider | HHRR Operations | N/A
15 | Mutual Company Registration | Register the work center in the Mutual Company for insurances and medical cover | Once the employees are registered | Health and safety manager & General Manager | HHRR Operations | N/A
16 | PPE's | Ensure that It is purchase and delivery of Personal Protective Equipment to the employees. | 30 | General Manager & Head Of Department | HHRR Operations | H&S management software tool (in the countries where it is available)
17 | Medical Examinations | Conducting medical examinations for all employees. | Once the employees start with the operative | Health and safety manager & General Manager | HHRR Operations | N/A
18 | Emergency Group | Define the Emergency Group (EG) and designate its members for the emergency measure | 10 | Health and safety manager & General Manager | HHRR Operations | H&S management software tool (in the countries where it is available)
19 | Training in Emergencies | Impartition of Emergency Training for the Hotel Emergency Group | 15 | Health and safety manager & External prevention service & Internal prevention service | HHRR Operations | N/A
20 | Emergency Drill | Perform emergency drill. | 15 | General Manager & Health and safety manager & External prevention service & Internal prevention service | HHRR Operations | N/A
21 | Outsourcing Services | In the case of outsourcing (housekeeping, F&B): perform the required actions by coordinating business activities regulations. | Once the employees start with the operative | Health and safety manager & General Manager | HHRR Operations | H&S management software tool (in the countries where it is available)
22 | Employees Structure | Personnel Administration will create the structure to be able to register employees | 15 | Payroll Manager | HHRR Administration | SAP
23 | Center Creation | Sincee the hotel is created in SAP and has an ID, It will proceed to create it in M4 in order to calculate and pay the payroll of all employees. Depending on the type of hotel (Property, Management, Franchise), a different creation and management process is needed | 15 | Payroll Manager | HHRR | M4, WinLohn, Raed, etc.
24 | Hotel Staff | Regional will notify the employees that will form the hotel staff. These employees will be from the previous property, transferred from other hotels or new hires. | 10 | Regional Director & Payroll Manager | HHRR | SAP, M4, WinLohn, Raed, etc.
Business Processes - Operations

## Legal
Process: Preopening Hotel
Process Owner: SVP Operations |  |  | Process Leader: Responsible of the involved area
Order | Task | Task Description | When (days before opening) | Responsible | Departments Involved | Tools
1 | Hotel contract signed | Hotel contract signed supervision | The signature's contract time | Legal Director | Legal Assets | N/A
2 | Opening Communication | Send the signed contract confirmation e-mail to all BU & HQ departments involved: Compulsorily to SVPs / VPs at Headquarters (Finance, Operations, Marketing, Commercial, Internal Audit, Legal, HR, Assets & Development), BU Management Committee. Moreover, if the Operations Regional or the General Manager are involved in the process, the BU Operations Director is responsible for providing the information. | Once the contract is signed | Legal Director | All company areas | E-Mail
3 | Licenses and permits | Municipal building permit | Depends on the country and type of contract and permits | Project Manager | Legal PCM&E | N/A
4 | Licenses and permits | Municipal activity license and opening. Hotel and F&B activity | Depends on the country and type of contract and permits | Project Manager | Legal PCM&E | N/A
5 | Hotel registration in Tourism Administration | Hotel registration in Tourism Administration | Depends on the country and type of contract and permits | General Manager | Operations Legal | N/A
6 | Power of attorney | Ask for a power of attorney for the General manager of the Hotel that shall be granted by the Hotel Owner or by the Lessee. | 180 | Operations - GM | Legal Operations | N/A
7 | Hand over | Hand over in case that it has been postponed until opening | 0 | Legal Director | PCM&E Legal | N/A
Business Processes - Operations