## Takeover_Fast-track
FAST-TRACK TAKEOVER MILESTONES |  |  | HOTEL NAME
Hotel Preopening Process |  |  | Project/Preopening Team Leader
MINOR HOTELS EUROPE & AMERICAS |  |  | LIVE SALE DATE | 2026-08-01
|  |  | OPENING DATE | 2026-11-01
KEY FOCUS POINTS | • Prioritize Critical Tasks • Ensure sales channels, website, and systems are ready at least 30 days before opening; pre-sales must start 60–30 days prior, depending on project duration • Execute multiple tasks simultaneously where possible • Use existing systems and personnel to accelerate processes • Ensure constant and clear communication among all stakeholders
CRITICAL TASKS | TAKEOVER MILESTONES | Responsibility | Involvement | Days before takeover 60-46 | Days before takeover 45-31 | Days before takeover 30-16 | Days before takeover 15-1 | TAKEOVER DAY/WEEK | POST-TAKEOVER (timing as per contract)
PRE-SIGNING PREPARATION (to be initiated by Expansion or local Ops if a fast-track opening is anticipated)
1 | Notify relevant stakeholders of potential fast-track opening | Expansion/Operations BU | Expansion, Operations BU | as soon as a fast-track opening is suspected
2 | Form the preopening team and communicate | Expansion/Operations BU | Expansion, Operations BU | as soon as a fast-track opening is suspected or immediately after contract signature
3 | Revenue configuration template (MR&RS). Gather the following data to complete the document, open a JIRA ticket, and share it with all relevant departments: - Room Number - Floor - Room Type - Bedding Type - Information about View, Terrace, etc. - Square Meters | Expansion/Operations BU | Revenue | as soon as a fast-track opening is suspected or as soon as possible
4 | Live sale date: agree on the date to start selling the hotel on the web, channels, and systems, and communicate this to RO E-Commerce, Commercial Systems, and Distribution. | Revenue Systems, BU Distribution Manager, BU E-Commerce Manager, Operations | Revenue, Distribution, E-Commerce, Operations | as soon as possible
5 | Hotel bank account and payment terminals setup. The payment gateway (if applicable) requires lead time for Treasury and Planet to set up the MIDs (Merchant IDs) and request terminals. Coordinate with the property to gather necessary information for the setup, paying special attention to the requirements for AMEX due to the extensive documentation needed. | Expansion/Operations BU | Expansion, Operations BU | as soon as a fast-track opening is suspected or as soon as possible
6 | Adyen merchant account: send credit card and bank account information to the E-Commerce team to open an Adyen merchant account. | Treasury Director RO | E-Commerce | as soon as a fast-track opening is suspected or as soon as possible
7 | Assess current distribution channels and define integration needs | Expansion/Operations BU | Distribution, E-Commerce, Revenue | as soon as a fast-track opening is suspected or as soon as possible
8 | Evaluate feasibility of soft opening without brand, using hotel’s existing systems | Expansion/Operations BU | Expansion, Operations BU | as soon as a fast-track opening is suspected or as soon as possible
SETUP, STRATEGIC PLANNING & IMPLEMENTATION (all tasks from contract signature to final handover)
9 | Contract signing and communication | Legal Director | Assets | at contract signature
10 | Definition of required hardware infrastructure | Infrastructure Manager |  | as soon as possible
11 | Obtain necessary licenses | Project Manager, Hotel GM | PCM&E, Legal | x
12 | Creation of the Company Center (send MD Company_Center Template via JIRA): Onyx model, Shared Services Center, DFM and SAP MM inclusion | Administration Director BU, IT BackOffice Manager | IT Applications | x
13 | Develop and load MH E&A web content |  |  | x | x | x | x
14 | Profile switch for OTAs: provide official document from Regional Office confirming new ownership of hotel profiles. | DCM / GDS | Sales | x | x | x | x
15 | Sales activation & communication | Hotel GM, Operations, Revenue Manager | Sales | x | x
16 | Master Data Management: create essential materials | SAP MM Key User, MDM team | IT Back Office |  | x
17 | Gather legal information for Registration Form | Legal Director | IT Applications |  | x
18 | Develop and start executing the Strategy Action Plan for sales and marketing | Regional Director of Sales, Director Business Development |  |  | x
19 | Personnel Hiring: General Manager | Regional Operations | People |  | x
20 | Personnel Hiring: Revenue Manager | Regional Operations | People |  | x
21 | Establish Compset and pricing | Regional Director of Sales, Director Revenue Manager | Operations |  | x
22 | Revenue positioning: define revenue strategies | Regional Director of Sales, Director Business Development, Director Revenue Manager, Hotel GM |  |  | x
23 | OTB & Pick-Up management: determine who will handle bookings and identify the system in which they will be entered if our system is not yet operational | Regional Director of Sales, Director Revenue Manager | Operations |  | x
24 | Implement procurement processes | Procurement | Business Processes MM |  |  | x
25 | Personnel Hiring: Heads of Departments | Hotel GM, Maintenance Regional | People |  |  | x
26 | Ensure hotel departments are operational | Regional Operations |  |  |  | x
27 | Load content into channels, Duetto, TMS, IBT, etc. | DCM / GDS | Sales |  |  | x
28 | Arrange for professional photo shooting of hotel photos | Marketing Director |  |  |  | x
29 | Configure tools to activate such as TMS4L, FastPass, etc. | Marketing Director, Hotel GM | IT, Loyalty, Business Processes |  |  | x
30 | Set up marketing campaigns | Marketing Director |  |  |  | x
31 | Prepare generic & hotel information brochures | Marketing Director |  |  |  | x
32 | Inventory of current contracts: translate local language contracts if needed | Commercial |  |  |  | x
33 | Complete the 'Excel Masterdata' template with hotel information and submit it to cro.tmscontect@minor-hotels.com for inclusion in the TMS Call Center. | Front Office Manager, Hotel GM | CRO |  |  |  | x
34 | Personnel Hiring: complete hiring of remaining staff | Hotel GM | People |  |  |  | x
35 | Conduct training sessions for systems, processes, and loyalty programs | Business Processes-Operations, Loyalty RO |  |  |  |  | x
36 | Arrange necessary Corporate insurance | Project Manager, Hotel GM | Operations, PCM&E, Legal |  |  |  | x
POST-TAKEOVER (eventual system migration and brand implementation)
37 | Operate under existing systems (if applicable) during soft opening phase | Operations | [6 empty] | x
38 | Plan and execute system migration to company platforms (PMS, CRS, RMS, etc.) | IT | [6 empty] | x
39 | Coordinate brand onboarding and training with hotel team | Marketing - Brand | People | [5 empty] | x
40 | Launch brand identity (signage, digital presence, guest experience standards) | Marketing - Experience | PCM&E | [5 empty] | x