## Takeover_Standard
STANDARD TAKEOVER MILESTONES |  | HOTEL NAME
Hotel Preopening Process |  | Project/Preopening Team Leader
MINOR HOTELS EUROPE & AMERICAS |  | LIVE SALE DATE | 2026-08-01
|  | OPENING DATE | 2026-11-01
KEY FOCUS POINTS | • Prioritize Critical Tasks • Ensure sales channels, website, and systems are ready at least 30 days before opening; pre-sales must start 60–30 days prior, depending on project duration • Execute multiple tasks simultaneously where possible • Use existing systems and personnel to accelerate processes • Ensure constant and clear communication among all stakeholders
CRITICAL TASKS | TAKEOVER MILESTONES | Details | AREA | Responsibility | Involvement | > 4 months prior | >3 months prior | >2 months prior | 56 days prior | 49 days prior | 42 days prior | 35 days prior | 28 days prior | 21 days prior | 14 days prior | 7 days prior | Opening Day/Week | 1 month after | 2 months after | 3 months after
1 | Notify relevant stakeholders of potential takeover | Some initial tasks can and should be launched before the official signing, especially when the hotel is located in a country where we do not yet operate or if it is a complex property type. Early communication with key stakeholders is essential to ensure readiness. | Expansion | Expansion | Operations | as soon as takeover is suspected
2 | Contract signature & communication | Ensure the hotel contract is signed and share confirmation with all relevant stakeholders across BU and Regional teams. | Legal | Legal Director BU | Assets | at contract signature
3 | DISCOVERY management contract requirements | Ensure the property completes and signs the Minor Statement of Services (Order Form). | Marketing | CRM & Loyalty | CRM & Loyalty | at contract signature
4 | Preopening team & communication | Confirm preopening team structure and complete the communication template for distribution to all involved teams. | Operations | Operations BU | Operations | immediately after takeover signature
5 | Collect hotel data | Define inventory, room categories, and business mix. | Commercial | Revenue Manager | Operations, Sales | immediately after takeover signature
6 | Activate contract & competitor tools | Set up contract management systems and competitor intelligence platforms to support pricing and sales strategy alignment. | Commercial | Director of Sales | Sales | immediately after takeover signature
7 | Town Hall meetings | Plan and conduct Town Hall meetings with all staff to communicate the transition, introduce leadership, and address team members questions and concerns. | People | People Business Partner | Operations | immediately after takeover signature
8 | Communication to local market | Notify corporate, government, MICE, and wedding sectors about the rebrand. | Commercial | Director of Sales | Operations, Marketing, PR | alternatively, as soon as legally allowed
9 | Live sale date | Agree on the date to start selling the hotel on the web, channels, and systems, and communicate this to RO E-Commerce, Commercial Systems, and Distribution. | Commercial | Revenue Systems, BU Distribution Manager, BU E-Commerce Manager, Operations | Revenue, Distribution, E-Commerce, Operations | asap
10 | All departments to prepare Pre-Opening Budget (POB) |  | All company areas | All company areas | All company areas | x | x | x | x | x | x | x | x | x | x | x | x
11 | Creation of the Company Center | Send MD Company_Center Template via JIRA: Onyx model, Shared Services Center, DFM and SAP MM inclusion. | Finance | Administration Director BU | IT Applications, IT Back Office | x
12 | TMSforHotels setup | System configuration must be completed before revenue configurations can begin. Hotel setup in TMS form the Regional Office IT team takes at least 5 business days. | IT | IT Regional Office |  | x
13 | Send questionnaire for content creation | Collect hotel data for brand.com content. | Commercial | ECommerce Manager | Revenue, E-Commerce | x
14 | Submit filled questionnaires | Provide completed questionnaires to e-commerce team. | Operations | Hotel GM, FOM | Commercial - E-Commerce | x
15 | Upload strategy across channels | Upload strategy and public contracts across all channels. | Commercial | Revenue Manager |  | x
16 | Content creation & revision | Create and revise content for new hotel site, including image cropping and quality check. | Commercial | ECommerce Manager | Sales, Marketing, E-Commerce | x | x
17 | Organization chart | Create or update the hotel’s org chart to reflect key roles, reporting lines, and any structural changes under the new management. | People | People Business Partner | Operations | x | x | [8 empty] | x | x
18 | Create brand identity materials | Design logo, letterhead, stationery, and develop brand positioning and presentations. | Marketing | MarComms Manager | Sales, Operations | x | x
19 | Validate Comp Set & pricing strategy |  | Commercial | Revenue Manager | Operations, Sales | x | x
20 | Configure systems | Set up TMS4H, Duetto, Channel Manager, Group Quotation Tool, ORS, IDeaS (BAR upload), STR. | Commercial | Revenue Manager |  | x | x
21 | Operations excellence setup & onboarding | Appoint OE Leader, assess operations, set up systems, onboard HODs, plan improvements. | Operations | Hotel GM |  | x | x
22 | Verify and document opening financial positions | Opening balances of inventories and fixed asset register. | Finance | Finance |  | x | x | x
23 | Confirm and update licenses and insurance | Obtain mandatory licenses/permits, review operational licenses/insurance, update insurance policies to meet HMA requirements. | Finance | Finance |  | x | x | x
24 | Review land and construction-related obligations | Assess land tenure, construction contracts, municipal tax obligations, review/update capital expenditure programs. | Finance | Finance |  | x | x | x
25 | People audit & documentation review | Audit team members records and review all HR documentation (JDs, SOPs, contracts) for accuracy and compliance. | People | People Business Partner | Operations | x | x | x
26 | People operations review & alignment | Review compensation, benefits, leave accruals, and HR systems to identify gaps and align with Minor Hotels standards for operational readiness. | People | People Business Partner | People - Business Partner | x | x | x | x
27 | Conduct balance sheet review and prepare adjustments | AR/AP, accruals, team member benefits, inventory, bad debt provisions, accrual reversals, inventory write-offs, cancellation of contracts, insurance, legal claims, litigation. | Finance | Finance |  | x | x | x | x
28 | Verify legal and tax compliance | Confirm tax/VAT obligations, verify legal entity details, ensure compliance with local/juristic laws, prepare critical date list for tax/reporting. | Finance | Finance |  | x | x | x | x
29 | Review and finalize legal and operational agreements | Review HMA, JVA, funding agreements, finalize contracts/licenses/policies, maintain monitored schedule, review supplier contracts, develop standard templates. | Finance | Finance |  | x | x | x | x | x
30 | Finance team structure and onboarding | Review organization structure, headcount, job descriptions, performance, identify gaps, recruit new team members, conduct induction, distribute updated job descriptions/task lists, implement training plan, onboard new FC. | Finance | Finance |  | x | x | x | x | x
31 | Translating content | Translate content for new hotel site. | Commercial | ECommerce Manager |  |  | x
32 | Image upload & cropping | Upload and crop images for new hotel site. | Commercial | ECommerce Manager |  |  | x
33 | IT Budget & Recommendations | Prepare IT budget proposal for PMS/S&C/POS replacements and provide recommendations on security, internet, Wi-Fi, and equipment. | IT | IT Manager | Operations |  | x
34 | IT Onsite Survey | Conduct onsite IT survey to assess infrastructure and readiness. | IT | IT Manager | Operations |  | x
35 | Brand alignment & onboarding coordination | Align team with brand via workshop, gap analysis, and onboarding. | Marketing | Marketing Brand Manager | People - University, Operations BU |  | x | x
36 | Create hotel factsheets and templates | Produce hotel/trade factsheets and design templates for onsite communication and banners. | Marketing | MarComms Manager |  |  | x | x
37 | Update banking and cash handling | Review/update banking procedures, signature matrix, cash-in-transit process, open/update operational bank accounts, review petty cash policy, engage credit card banking providers. | Finance | Finance |  |  | x | x
38 | Review manning structure | Align staffing with business demand and operating hours across departments. | Operations | Hotel GM | People |  | x | x
39 | Enforce SOPs & job descriptions |  | Operations | Hotel GM | People |  | x | x
40 | Implement brand standards | Uniforms, guest supplies, printed materials, room and outlet brand guidelines. | Operations | Hotel GM | People |  | x | x
41 | Inspect facilities | Inspect rooms, public areas, outlets, kitchens, canteen and identify urgent repairs. | Operations | Hotel GM |  |  | x | x
42 | Assess key positions in 1:1 meetings | Hold individual meetings with key staff to evaluate performance and alignment with the new operation. | People | People Business Partner | Operations |  | x | x | x
43 | Review and manage compensation and benefits | Evaluate salary structure, benefits grid, expat/senior contracts, process final pay for departing execs, identify payroll/benefits liabilities, arrange medical insurance. | Finance | Finance |  |  | x | x | x
44 | Engage external partners | Review, select, and engage external auditors, legal advisors, pension fund providers. | Finance | Finance |  |  | x | x | x
45 | Implement financial controls and procedures | Establish controls for AP, AR, cashiering, night audit, cost control, storekeeping, set up credit approval procedures, issue procedures for income transfer from advance deposits. | Finance | Finance |  |  | x | x | x
46 | Load contracts & OCRs | Screen Minor clients for in-year additions. | Commercial | Director of Sales |  |  | x | x | x | x
47 | Review and prepare IT systems for transition | Assess IT systems (PMS, POS, back office), configurations, interface capabilities, develop contingency plan, prepare migration plan, review payroll/time attendance systems, F&B checks, guest folio templates. | IT | IT Manager | IT Regional Office |  | x | x | x | x
48 | Set up financial systems and reporting | Implement general ledger system and Hyperion (only for consolidation perimeter hotels), train team, convert system reports to Minor Hotels format, roll out MINT Finance Policies, LSOPs, reporting templates, establish accounting forms/reports, implement Minor Hotels monthly report format. | Finance | Finance | IT Back Office |  | x | x | x | x
49 | People reporting (weekly/monthly) | Generate and share regular reports on key HR metrics to support decision-making and track team performance during the transition. | People | People Business Partner | Operations |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
50 | Create hotel in Content Channel Manager & TPWs | Set up hotel in content channel manager and TPWs. | Commercial | ECommerce Manager |  |  |  | x
51 | Go-Live of new Hotel website |  | Commercial | ECommerce Manager |  |  |  | x
52 | Launch paid campaigns | Activate paid campaigns to drive traffic. | Commercial | ECommerce Manager |  |  |  | x |  |  |  | `
53 | Set up reservations | Configure email, call accounting, and 7 Steps training. | Commercial | Revenue Manager | Operations, Sales, PR, Marcom |  |  | x
54 | Support Revenue Manager recruitment |  | Commercial | Revenue Manager | Operations, People |  |  | x
55 | Conduct training | Train on Revenue, Commercial Philosophy, Hunters, Organizers. | Commercial | Revenue Manager |  |  |  | x
56 | Activate BGR sales | Deploy brand-aligned quotation templates. | Commercial | Revenue Manager |  |  |  | x
57 | Launch reporting | Initiate Strategic Sales Meetings and structure. | Commercial | Revenue Manager |  |  |  | x
58 | Prepare and manage inventory and procurement | Review procurement procedures, identify obsolete branded items, prepare opening inventories/cash floats, review FF&E/OSE master lists, manage branded item replacement/credit notes. | Finance | Finance |  |  |  | x
59 | Employer branding & team communication | Install BOH signage and establish regular team communication to reinforce brand culture and engagement. | People | People Business Partner | Internal Communication, Operations |  |  | x | x | x
60 | Email Audit & Deployment | Audit email accounts for Office 365 licensing and deploy new email accounts. | IT | IT Manager | Operations |  |  | x | x | x
61 | Review/Recruit 15 key positions | Evaluate current candidates or initiate recruitment for the 15 most critical roles to ensure leadership and operational readiness post-takeover. | People | People Business Partner | Operations |  |  | x | x | x | x | x | x
62 | Contact OTB business | Advise groups, weddings, and corporate clients about the rebrand. | Commercial | Director of Sales |  |  |  | x | x | x | x | x | x | x | x | x | x
63 | Align internal controls | Review and align internal controls with Finance and Regional Office. | Operations | Hotel GM | Finance |  |  |  | x | x | x
64 | Align sales materials | Update contracts, proposals, and templates to reflect new brand identity. | Commercial | Director of Sales |  |  |  |  | x | x | x | x | x | x | x | x
65 | Conduct commercial update calls | Deploy segment action plans. | Commercial | Director of Sales | [5 empty] | x | x
66 | Backup & Application Configuration | Set up backup system and configure application renaming. | IT | IT Manager | [5 empty] | x | x | x
67 | Review room allocations & costs | Review room allocations, analyze costs (utilities, supplies, inventory). | Operations | Hotel GM | [5 empty] | x | x | x
68 | Inventory & warehouse restructuring | Restructure warehouse inventory, eliminate dead capital, review store items. | Operations | Hotel GM | Finance - Procurement |  |  |  |  | x | x | x
69 | Preventive cleaning programs | Implement preventive and major cleaning programs. | Operations | Hotel GM, Housekeeping Manager | [5 empty] | x | x | x
70 | Coordinate signage and image preparation | Coordinate signage and OPE list, retouch/upload images to Leonardo with consent forms. | Marketing | MarComms Manager | [5 empty] | x | x | x | x
71 | Safety training | Deliver mandatory safety training sessions to ensure all team members understand health, safety, and emergency procedures. | People | BU Health & Safety Manager | Operations | [5 empty] | x | x
72 | Live of the preopening site | Launch preopening site on old website. | Commercial | ECommerce Manager | Revenue, Sales | [5 empty] | x | x
73 | Train teams on PMS | Train operations teams on PMS and related systems. | Operations | Business Processes | [6 empty] | x | x | x
74 | F&B brand guidelines & menus | Introduce F&B brand guidelines, engineer menus and pricing. | Operations | F&B Manager | [6 empty] | x | x | x | x
75 | Onboarding & brand orientation | Design and deliver onboarding sessions for all staff, including brand values, service standards, and operational expectations to ensure alignment with MH culture from day one. | People | People University | Operations | [5 empty] | x | x | x | x
76 | Coordinate sales training | Organize e-learning for Minor Global Sales Force. | Commercial | Director of Sales | [6 empty] | x | x | x | x
77 | Prepare website content and offers | Prepare content, images, and opening offer for VRIV and brand.com. | Marketing | MarComms Manager | [6 empty] | x | x | x | x
78 | HSIA Interface Setup | Configure HSIA interface with Epitome PMS (Username/Password). | IT | IT Manager | [7 empty] | x | x
79 | Migrate Lanyon access | Sign up for RFPs. | Commercial | Director of Sales | Operations, Revenue | [6 empty] | x | x | x | x
80 | Implement reporting tools | Set up Group Pace, Wedding Pace, and Monthly Sales Reports. | Commercial | Director of Sales | Operations, Revenue, Marketing, PR | [6 empty] | x | x | x | x
81 | Setup and configuration of IBE |  | Commercial | ECommerce Manager | IT, Revenue, Operations | [6 empty] | x | x | x | x
82 | UAT and testing of the Booking engine |  | Commercial | ECommerce Manager | Revenue | [6 empty] | x | x | x | x
83 | Create GRC | Establish Group Room Control. | Commercial | Director of Sales | PR, Marcom | [7 empty] | x | x | x
84 | Engage with GSO/GSA network | Organize cluster team visits. | Commercial | Director of Sales | [8 empty] | x | x | x
85 | Service simulations | Conduct service simulations for FO, Concierge, HSKP, kitchen and outlets. | Operations | Hotel GM, Housekeeping Manager, F&B Manager | [8 empty] | x | x | x
86 | F&B activities planning | Plan F&B activities (July-Dec), including year-end events. | Operations | F&B Manager | [8 empty] | x | x | x
87 | HACCP & food safety | Implement HACCP & Food Safety Management System with Ecolab. | Operations | F&B Manager | Finance - Procurement | [7 empty] | x | x | x
88 | Deploy task force & sales blitzes | Organize sales blitzes across local, regional, and key metropolitan areas. | Commercial | Director of Sales | [8 empty] | x | x | x | x
89 | Task Force planning & deployment | Coordinate and deploy task force support to ensure operational continuity and training during the transition. | People | People Business Partner | Operations | [7 empty] | x | x | x | x | x
90 | Launch media and social campaigns | Launch owned, paid, and earned media campaigns; take over and update social and location accounts. | Marketing | MarComms Manager | [8 empty] | x | x | x | x | x
91 | Security setup & drills | Assess security coverage, implement SOPs, conduct fire drill simulation. | Operations | Hotel GM | People | [7 empty] | x | x | x | x
92 | Plan PR strategy | Prepare press release, press kit, and media FAM trip. | Commercial | Director of Sales | Operations, Revenue, Marketing, PR | [8 empty] | x | x | x
93 | Live of Booking Engine, GDS & Channel Manager | Launch booking engine, GDS configuration, and channel manager. | Commercial | ECommerce Manager | Sales, Revenue, IT | [8 empty] | x | x | x
94 | PPC campaign preparation & live | Prepare and launch "Pay-Per-Click" campaigns. | Commercial | ECommerce Manager | Revenue, Sales, IT, Marcom | [8 empty] | x | x | x
95 | Take over social media & local market campaign |  | Commercial | ECommerce Manager | Sales, Revenue | [9 empty] | x | x
96 | Start SEO setup & configurations |  | Commercial | ECommerce Manager | Sales, Revenue, IT | [9 empty] | x | x | x | x
97 | Live of new brand website (English and local language) |  | Commercial | ECommerce Manager | Operations, Sales, Revenue, PR& Marcom | [10 empty] | x | x
98 | Send opening announcement eDM | Distribute email campaign to announce hotel opening. | Marketing | MarComms Manager | Sales, Operations, PR | [11 empty] | x
99 | Coordinate transition of guest programs (VIP cards, loyalty programs, spa/health club memberships) | Review/update membership inclusions. | Finance | Finance | [12 empty] | x
100 | Execute takeover day and post-go-live tasks | Execute takeover day cut-over (systems, reports, guest in-house, inventory, float counts), submit first-day operational reports, complete income audit checklist, update actual expenses in POB module, complete first monthly/quarterly cycles, confirm systems go-live (stationery, credit cards, merchant IDs), transfer proprietary info. | Finance | Finance | [12 empty] | x | x
101 | Provide daily support post-opening |  | Commercial | Revenue Manager | [12 empty] | x | x
100 | Prepare and align financial planning | Prepare business forecast (remainder of year, OTB, working capital), implement Minor Hotels forecasting procedures, prepare Year 1 operational budget, review proforma projections from HMA/JVA, prepare conversion/rebranding budget, develop 5-year financial plan (P&L, balance sheet, Capex, ROI). | Finance | Finance | [12 empty] | x | x
101 | Introduce teams and align operations | Introduce Finance, Purchasing, and IT teams to Minor Hotels policies, implement meetings schedule, assess accounting office setup (access, hardware, functionality), review A/P cheque usage. | Finance | Finance | [12 empty] | x
Note on C37: HMA: Hotel Management Agreement JVA: Joint Venture Agreement
Note on C66: FF&E: Furniture, Fixtures, and Equipment OSE: Operating Supplies and Equipment